## Arms Sale Backlog
Date of Congressional Notification | Capability Sold | Dollar Value (In Millions) | Weapon Category | Details of Capabilities | Status as of April 30, 2026 | DSCA Sale Link
2017-06-29 | AGM-154C Joint Standoff Weapon | 185.5 | Munition | 56 AGM-154C JSOW Air-to-Ground Missiles plus various spares and support services. | Reporting from February 2024 indicated a contract signed with RTX (formerly Ratheon) for 50 AGM-154Cs for $68.4 million to be delivered by March 2028: https://www.taipeitimes.com/News/front/archives/2024/02/05/2003813098. MND reports from early and mid 2024 indicate a delivery date of 2026 for the missiles. Which suggests that the contract may include post-delivery support services or equipment. The MND labeled the JSOW, TOW, and F-16 as "delayed" in October 2024. https://www.cna.com.tw/news/aipl/202410070212.aspx. A March 2025 MND report to the LY said there were delays in AGM-154C delivery. As of March 2025, the F-16 Block 70/72s and the AGM-154Cs are the only two FMS cases that MND considers "delayed" https://www.taipeitimes.com/News/taiwan/archives/2025/03/21/2003833811. Taiwan press reporting citing an MND report to the LY in June 2025 says that delivery of AGM-154C was delayed from 2023 to 2026: https://def.ltn.com.tw/article/breakingnews/5080325. October 2025, AGM-154C mentioned as one of three delayed arms sales in testimony by Defense Minister Wellington Koo to members of the LY, https://www.cna.com.tw/news/aipl/202510310278.aspx. December 2025: MND report to the LY reiterates AGM-154C as s delayed arms sale. | https://media.defense.gov/2024/Dec/18/2003615461/-1/-1/0/TECRO_16-73.PDF
2017-06-29 | Mk 48 Heavyweight Torpedoes (Announced June 2017) | 250 | Munition | 46 announced in the DCSA sale. SIPRI dataset shows 28 torpedoes in a 2018 sale and 18 in 2020. | Reporting from May 2023 indicated delivery of 46 Mk-48 torpedoes would take place in 2025: https://www.taipeitimes.com/News/taiwan/archives/2023/05/07/2003799314. SIPRI 2024 data indicates delivery of 5 torpedoes in 2023, with full delivery planned by 2026. A September 2024 report from Taiwan News indicates that delivery was supposed to be completed in 2028 but was extended to 2030, https://www.taiwannews.com.tw/news/5932938. Also see this report from Liberty Times: https://def.ltn.com.tw/article/breakingnews/4793577. SIPRI data from March 2025 continues to say that 5 HWTs have been delivered as of 2023. Taiwan's indigenous submarine program, the primary platform to use the MK-48, is running behind schedule on sea trials. This might lead to a knock-on effect of delaying torpedo delivery, but this is not certain, https://www.taipeitimes.com/News/taiwan/archives/2025/04/30/2003836087. The 2026 defense budget request to the LY indicates that 4 training torpedoes will be delivered next year, per https://udn.com/news/story/10930/8974333. September 2025: press reports indicate that Taiwan woulld receive 14 torpedoes in 2027 and 10 torpedoes in 2028, https://www.taipeitimes.com/News/front/archives/2025/08/31/2003842965. October 2025 in a hearing at the LY, Defense Minister Koo mentions the torpedoes as an example of a delayed arms sale. This is the first time that MND has labeled the torpedoes as delayed, a June 2025 letter to the LY on arms sale delivery status only had AGM-154C and F-16 as delayed, https://www.cna.com.tw/news/aipl/202510310278.aspx. December 2025: Report by MND to LY on arms sale status categorizes the Mk-48 as a delayed arms sale. | https://media.defense.gov/2024/Dec/18/2003615459/-1/-1/0/TECRO_16-69.PDF
2019-07-08 | M1A2T Abrams Tanks | 2000 | Traditional | 108 tanks plus related ammunition, sensors, and other support equipment. | Reporting from August 2023 indicated Taiwan will begin receiving a shipment of 38 tanks in 2024, with delivery expected to be complete in 2026: https://www.thedefensepost.com/2023/08/23/taiwan-abrams-tanks-us/. SIPRI Arms Transfer Database data from March 2024 indicates final delivery expected in 2026. March 2024 SIPRI data indicates 2 tanks were delivered in 2022, likely for initial familiarization. MND report from June 2024 says that 14 Abrams tanks are conducting "inspector training" at US bases, could be referencing a quality testing before tanks are delivered to Taiwan. A September 2024 report from CNA says that Taiwan will receive its first batch of 38 M1A2T tanks in December 2024, https://focustaiwan.tw/politics/202409220012. The first batch of 38 Abrams tanks arrived in Taiwan around December 14, 2024: https://x.com/JaimeOcon1/status/1868509648208445769. Reports from February 2025 indicate that classroom training on the Abrams tanks has begun, with soldiers who received initial familiarization training teaching other tankers on how to use the tanks, https://thedefensepost.com/2025/02/04/taiwanese-army-training-abrams/. MND report to the LY in May 2025 says that delivery of the Abrams is proceeding as scheduled, second batch of 42 tanks should arrive by end of second quarter of 2025, final batch of 28 tanks expected to arrive by first quarter 2026: https://defence-blog.com/taiwan-nears-full-deployment-of-us-made-abrams-tanks/. In July 2025 the second batch of 42 tanks arrived in Taiwan as scheduled, https://focustaiwan.tw/politics/202507280005. February 2026: Taiwan press reports citing MND that final 28 Abrams tanks were having shipping arrangements made and should arrive in Taiwan sometime before the end of March 2026, https://www.taipeitimes.com/News/taiwan/archives/2026/02/02/2003851632. March 2026: MND officials stated that the final batch of 28 Abrams are “at sea” enroute to Taiwan. Further statements indicated delivery either at the end of March or in April. https://focustaiwan.tw/politics/202603100021. April 2026: MND confirmed delivery of last 28 tanks out of 108 total at Port of Taipei. https://def.ltn.com.tw/article/breakingnews/5417171. | https://media.defense.gov/2024/Dec/18/2003615455/-1/-1/0/TECRO_19-22_0.PDF
2019-08-20 | F-16C/D Block 70 | 8000 | Traditional | 66 aircraft plus various avionics, spare engines, and other supporting equipment. | Reporting from May 2023 indicated Taiwan will receive all 66 aircraft by 2026: https://www.reuters.com/business/aerospace-defense/taiwan-says-software-problems-delaying-new-f-16-deliveries-2023-05-25/. MND reports from early 2024 said that Taiwan was anticipating taking delivery of first new F-16s in 2024, but that only two would be delivered instead of a larger initial tranche: https://focustaiwan.tw/politics/202406170007. Taiwanese press reported that its first pair of newly built F-16s would arrive at the end of September 2024, but as of September 30 there was no additional reporting to confirm arrival: https://www.taipeitimes.com/News/taiwan/archives/2024/09/13/2003823728. As of December 31, 2024 there was no reporting or statements from MND indicating that initial delivery of the F-16s had occurred despite reporting earlier in 2024 that a first tranche would arrive by the end of 2024. Reporting from January 2025 quotes Defense Minister Wellington Koo saying the first jets will leave the factory in March 2025, https://taiwannews.com.tw/news/6017753. In March 2025 the first completed F-16 Block 70/72 for Taiwan rolled off the assembly line, and senior Taiwanese officials were present at a ceremony to mark the occaison: https://www.reuters.com/world/asia-pacific/senior-taiwan-defence-official-visit-us-fighter-jet-ceremony-2025-03-26/. Taiwan press reporting from June 2025 citing an MND report to the LY says that Taiwan expects to receive 10 airframes by the end of 2025, and all 66 by the end of 2026: https://def.ltn.com.tw/article/breakingnews/5080325. MND in June 2025 report is optimistic that all 66 aircraft will arrive in Taiwan by the end of 2026 despite delays in delivery of the first aircraft: https://www.taipeitimes.com/News/front/archives/2025/06/20/2003838921. September 2025 press report states that first two aircraft are expected to arrive in Taiwan around October 10th, Taiwan's National Day, however the ROC Air Force said this was a rumor: https://www.taipeitimes.com/News/taiwan/archives/2025/09/10/2003843542, and https://def.ltn.com.tw/article/breakingnews/5179787. October 2025 members of the LY question premier Cho about delivery delays for US arms sales, with the F-16 case being a focal point. Cho told lawmakers that they expect F-16s to begin arriving in early 2026, but did not give an answer on how many would arrive in 2026 or when full delivery would be complete: https://www.cna.com.tw/news/aipl/202510310278.aspx. December 2025: MND report to the LY on arms sale status repeated earlier assertion that F-16s are one of three delayed arms sales. Photographs from the United States showed F-16s completing ground taxiing tests, and CNA reports that flight tests were supposed to begin before the end of 2025, https://www.cna.com.tw/news/aipl/202512200160.aspx. January 2026: USAF awarded a contract modification for production of F-16 Block 70 training simulators that are a component of this arms sale. Work expected to complete in August 2028, https://www.war.gov/News/Contracts/Contract/Article/4393248/contracts-for-jan-29-2026/. February 2026: MND expects F-16s to begin arriving in 2026, but the pace of arrivals/deliveries is not clear, https://www.taipeitimes.com/News/taiwan/archives/2026/02/09/2003852027. March 2026: Taiwanese officials attended an Acceptance Check Flight in the U.S. for the first F-16 airframe. Minister Koo also stated to press that the first F-16 could arrive as early as September 2026. https://mna.mnd.gov.tw/news/detail/?UserKey=2d482d7e-ab69-45ce-b6c3-cc223c4f25f1. April 2026: Lockheed CFO Evan Scott noted in earnings call that production had “issues during the flight test” but they are “back on track” and deliveries of aircraft to Taiwan and Morocco would begin soon. https://www.fool.com/earnings/call-transcripts/2026/04/23/lockheed-martin-lmt-q1-2026-earnings-transcript. | https://media.defense.gov/2024/Dec/18/2003615456/-1/-1/0/TECRO_19-50.PDF
2020-05-20 | Mk 48 Heavyweight Torpedoes (Announced May 2020) | 180 | Munition | 2017 arms sale for 46 torpedoes was later reduced. This 2020 sale corrects for that reduction and brings the total Mk-48 number back to 46. | Reporting from May 2023 indicated delivery of 46 Mk-48 torpedoes would take place in 2025: https://www.taipeitimes.com/News/taiwan/archives/2023/05/07/2003799314. SIPRI 2024 data indicates delivery of 5 torpedoes in 2023, with full delivery planned by 2026. A September 2024 report from Taiwan News indicates that delivery was supposed to be completed in 2028 but was extended to 2030, https://www.taiwannews.com.tw/news/5932938. Also see this report from Liberty Times: https://def.ltn.com.tw/article/breakingnews/4793577. SIPRI data from March 2025 continues to say that 5 HWTs have been delivered as of 2023. Taiwan's indigenous submarine program, the primary platform to use the MK-48, is running behind schedule on sea trials. This might lead to a knock-on effect of delaying torpedo delivery, but this is not certain, https://www.taipeitimes.com/News/taiwan/archives/2025/04/30/2003836087. The 2026 defense budget request to the LY indicates that 4 training torpedoes will be delivered next year, per https://udn.com/news/story/10930/8974333. September 2025: press reports indicate that Taiwan woulld receive 14 torpedoes in 2027 and 10 torpedoes in 2028, https://www.taipeitimes.com/News/front/archives/2025/08/31/2003842965. October 2025 in a hearing at the LY, Defense Minister Koo mentions the torpedoes as an example of a delayed arms sale. This is the first time that MND has labeled the torpedoes as delayed, a June 2025 letter to the LY on arms sale delivery status only had AGM-154C and F-16 as delayed, https://www.cna.com.tw/news/aipl/202510310278.aspx. December 2025: Report by MND to LY on arms sale status categorizes the Mk-48 as a delayed arms sale. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-12
2020-10-21 | AGM-84H SLAM-ER Missile | 1008 | Munition | 135 missiles plus some training munitions, spare parts, and test equipment. | Reporting from January 2023 indicated a "large quantity of unnamed long-range weapons" for the F-16V will be delivered by 2030. The SLAM-ER was not confirmed to be part of this package, but it is suspected to be part of the package: https://www.taiwannews.com.tw/en/news/4777553. December 2025: Taiwanese press reports citing a report by the LY's budget office indicate that the AGM-84H has been repeatedly delayed, with the dollar amount fluctuating over time. The press report suggests that there is no LOA for the missiles and therefore no accurate estimate on delivery timeline, https://def.ltn.com.tw/article/breakingnews/5273483 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-16
2020-10-21 | MS-110 Recce Pods | 367.2 | Traditional | Reconnaissance pod for manned aircraft. | Contract announcement from December 22, 2021 indicates a completion date of November 30, 2025, https://www.defense.gov/News/Contracts/Contract/Article/2882869/. According to March 2024 SIPRI data, 3 of 6 pods have been delivered as of the end of 2023, with full delivery occurring probably by 2025. A September 2024 report by Taipei Times says that the military had not received any MS-110 pods yet, but that the delivery was expected to be completed in 2025: https://www.taipeitimes.com/News/taiwan/archives/2024/09/17/2003823913. The March 2025 update to SIPRI's data said that 5 out of 6 systems were delivered. CNA report from June 2025 that cited MND sources says delivery of the pods should begin happening in 2025 in batches, unclear when final delivery will happen from the article: https://www.cna.com.tw/news/aipl/202506040126.aspx. In July 2025 Taiwan retired its last remaining RF-5E aircraft. It's recon role will be filled by MQ-9B drones and F-16s equipped with MS-110 pods, https://www.twz.com/air/taiwans-rf-5-tigergazer-reconnaissance-jets-have-retired. The 2026 defense budget report to the LY indicates that the remaining 5 pods will be delivered by next year, https://udn.com/news/story/10930/8974333. February 2026: Taiwan press report citing MND sources indicate that three MS-110 pods are expected to arrive by the end of 2026, https://www.taipeitimes.com/News/taiwan/archives/2026/02/09/2003852027 | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-14
2020-10-26 | Harpoon Coastal Defense System | 2370 | Asymmetric | 100 ground-based launchers, 25 radar trucks, and 400 Harpoon missiles. | In March 2022, a contract was finalized for delivery of the launchers, radar, and training equipment, which is expected to be completed in December 2028: https://www.defense.gov/News/Contracts/Contract/Article/2952403/. An April 2023 contract award announcement for 400 Harpoon missiles, which does not mention Taiwan by name but has the correct number of missiles and support equipment, puts delivery as March 2029: https://www.defense.gov/News/Contracts/Contract/Article/3356129/. A September 2024 report from Liberty Times says that an initial shipment of ground-launched Harpoon missiles were delivered on September 27, 2024. This delivery reportedly involved 32 launchers and 128 missiles: https://def.ltn.com.tw/article/breakingnews/4814390. Another Liberty Times article from September 28 mentions delivery of "equipment" for the systems but not not specify numbers of launchers or missiles. It gives a date of 2026 for the 32 launchers and 128 missiles: https://def.ltn.com.tw/article/breakingnews/4813892. March 2025 SIPRI data update reflects partial delivery of Harpoon equipment that is consisent with Taiwan press reports from September 2024. Unfreezing report by MND to LY in May 2025 indicates that 5 launcher vehicles and 1 radar truck were delivered to Taiwan in first half of 2025: https://def.ltn.com.tw/article/breakingnews/5030266. September 2025 press report indicates delivery of first batch of missiles is expected to occur before the end of 2025 ahead of establishment of the Navy's Littoral Combat Command on New Year's Day 2026: https://def.ltn.com.tw/article/breakingnews/5162742. October 2025 press report confirmed that Taiwan would receive first batch of Harpoon missiles to arm the HCDS systems in time for the Littoral Combat Command stand-up on January 1, 2026, however the number of missiles in this initial batch has not been confirmed https://focustaiwan.tw/politics/202510200015. February 2025: Press reports citing MND budget document indicate delivery of 100 additional Harpoon missiles by the end of 2026, https://www.taipeitimes.com/News/taiwan/archives/2026/02/09/2003852027. March 2026: U.S. DSCA Director Michael Miller confirmed in a House hearing that Taiwan has priority for delivery of HCDS over Saudi Arabia. https://foreignaffairs.house.gov/committee-activity/hearings/reforming-america-s-defense-sales-0. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-17
2020-11-03 | MQ-9B Unmanned Aircraft | 600 | Asymmetric | 4 MQ-9B Sea Guardian drones and associated sensors and support equipment | Contract announcement from May 1, 2023 indicates delivery of four MQ-9Bs and two ground stations will be completed on May 5, 2025: https://www.defense.gov/News/Contracts/Contract/Article/3380162/. Asecond contract award announcement from March 12, 2024 indicates final delivery in August 2027. A reporter from Taiwan's Central News Agency confirmed that the two contracts are for the purchase of 4 drones and 2 ground stations, meaning the purchase was divided across two contracts. https://www.defense.gov/News/Contracts/Contract/Article/3704846/. Reporting from Taiwanese press sources from August 2024 said that the first batch (presumably 2) would be delivered by 2026: https://www.taipeitimes.com/News/front/archives/2024/08/26/2003822773. In January 2025, the LY froze NT$500 million (US $15.25 million) from the budget until MND issued a report addressing the legislature's concern that all four MQ-9Bs would be stored in a single hanger, https://www.taipeitimes.com/News/taiwan/archives/2025/01/02/2003829528. Unfreezing report from MND to LY in May 2025 indicates that all four MQ-9Bs will arrive in Taiwan in 2026, https://def.ltn.com.tw/article/breakingnews/5030266. The 2026 defense budget report to the LY indicates that two drones will be delivered by next year, https://udn.com/news/story/10930/8974333. September 2025: press report indicates delivery of two drones in 2026 and remaining two in 2028, also states that the drones are optimized for maritime surveillance, https://www.taipeitimes.com/News/taiwan/archives/2025/09/09/2003843482. February 2026: Press report citing MND budget document indicates delivery of first 2 MQ-9s expected before the end of 2026, https://www.taipeitimes.com/News/taiwan/archives/2026/02/09/2003852027. March 2026: Taiwanese officials attended a “handover” ceremony in the U.S. for two of the expected four drones, clarifying that they expect to remain for further testing. LY testimony from MND officials also clarified that delivery is expected by the third quarter of 2026 and should not be delayed by ongoing conflict in the Middle East. https://mna.mnd.gov.tw/news/detail/?UserKey=ab3679b9-39ee-4408-b244-02333427452f, https://www.cna.com.tw/news/aipl/202603160124.aspx. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-18
2020-12-07 | Field Information Communications System | 280 | Asymmetric | Battlefield communication system. | Reporting from March 2022 indicated delivery sometime in 2025: https://www.taipeitimes.com/News/taiwan/archives/2022/03/12/2003774639. Unfreezing report from MND to LY in May 2025 indicates that FICS testing had successfully concluded in the US in early 2025, and first batch of equipment will arrive in Taiwan in the fourth quarter of 2025, https://def.ltn.com.tw/article/breakingnews/5035253. | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-19
2022-09-02 | Air-Launched Harpoon Missiles | 355 | Asymmetric | 60 AGM-84-L-1 air launched Harpoons plus associated spare parts and support equipment. | Report from January 2023 indicated that these missiles will be delivered by 2030: https://www.taiwannews.com.tw/en/news/4777553 | https://media.defense.gov/2024/Dec/18/2003615445/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-45%20CN.PDF
2022-09-02 | AIM-9X Block II Missiles | 86 | Munition | 100 AIM-9X sidewider missiles and four guidance unit kits. | Report from January 2023 indicated that these missiles will be delivered by 2030: https://www.taiwannews.com.tw/en/news/4777553. SIPRI March 2024 data also suggests delivery planned by 2030. CNA article from January 2025 says that Taiwan issued an E-Procurement report for NASAMs, which include AIM-9X missiles, with a completion date of 2034. However, it is possible that Taiwan would receive the missiles before the end of the contract window https://www.cna.com.tw/news/aipl/202501100287.aspx. On June 2, 2025, Raytheon received a $1.1 billion contract modification for production of approximately 2,000 AIM-9X missiles, including 1,050 for unspecified FMS customers. Contract will be completed by October 2028: https://www.defense.gov/News/Contracts/Contract/Article/4203613/. | https://media.defense.gov/2024/Dec/18/2003615446/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-46%20CN.PDF
2022-12-05 | PAC-3 MSE Interceptors | 882 | Asymmetric | 100 PAC-3 MSE Interceptors. Modification to a January 2010 arms sale of Patriot batteries and interceptors to Taiwan. Not reported in DSCA data. | Taiwan News report from January 2024 quotes MND saying deliveries to occur in batches between 2025 and 2026: https://www.taiwannews.com.tw/en/news/5079542. April 2025 news reports out of Taiwan say that ROCAF will form a fourth Patriot defense battalion in anticipation of deliveries of additional interceptors in 2025 and 2026, which matches the timeline reported in January 2024, https://www.taipeitimes.com/News/taiwan/archives/2025/04/24/2003835726. The article mentions "hundreds" of PAC-3 MSE, but the arms sale notified to Congress was for 100 interceptors. October 2025, press reports in Taiwan say that the military is looking into purchasing 4 additional Patriot batteries and 500 interceptors from the United States, however there has been no notification to Congress of such a modification, https://www.newsweek.com/us-security-partner-eyes-more-patriot-missiles-amid-chinas-threat-10833503. December 2025: Taiwan press report repeats previous plan for Taiwan to purchase additional interceptors and other Patriot equipment once the special procurement budget passes the LY, https://def.ltn.com.tw/article/breakingnews/5285157. January 2026: Lockheed Martin awarded a contract extension for inspection, recertification, and repair of PAC-3 missiles, work is expected to complete by June 2028, https://x.com/TaiwanMonitor/status/2014156501913338006. January 2026: Defense Department announces a new framework agreement to significantly ramp up PAC-3 interceptor production from 600 to 2,000 per year. February 2026: Press report citing MND sources states that delivery of an unspecified number of PAC-3 MSE interceptors occurred sometime in the first two months of 2026. This would be consistent with earlier reported delivery timelines, https://def.ltn.com.tw/article/breakingnews/5339813. March 2026: MND officials stated that ongoing delivery of 102 MSE missiles should not be affected by conflict in the Middle East. https://www.cna.com.tw/news/aipl/202603160124.aspx | https://www.govinfo.gov/content/pkg/CREC-2022-12-05/pdf/CREC-2022-12-05.pdf
2022-12-05 | HIMARS (Announced December 2022) | 520 | Asymmetric | DSCA notified Congress of a purchase of 18 additional HIMARS in December 2022, plus 144 GMLRS pods, 20 ATACMS pods, and support vehicles. | The HIMARS sale was increased from 11 to 29 launchers in 2022. Taiwan reporting from May 2023 citing MND sources said that delivery of first 11 HIMARS would be complete by 2025, while delivery of the 18 additional launchers would be completed in 2026: https://www.taiwannews.com.tw/en/news/4883328. SIPRI March 2024 data indicates the US also sold 864 GMLRS rockets as part of the plus-up. Unclear if GMLRS sale is individual rockets or pods (6 rockets per pod). March 2025 reporting on a report by MND to the LY says remaining HIMARS are expected to be delivered in 2026, which Taiwan regards as one year ahead of schedule: https://www.taipeitimes.com/News/taiwan/archives/2025/03/21/2003833811. Unfreezing report from MND to LY in May 2025 confirms that Taiwan has received 11 launchers and has received most but not all of the ATACMS from that FMS case. Delivery of second batch of launchers and munitions is on schedule. https://def.ltn.com.tw/article/breakingnews/5032541. October 2025, in testimony before the Legislative Yuan, senior Lai administration officials reiterated that HIMARS deliveries are ahead of schedule. This tracks with earlier reporting. December 2025: MND report to LY on arms sale delivery status repeats earlier assessment that this HIMARS sale is considered ahead of schedule. February 2026: Press report citing MND sources indicates that 18 HIMARS launchers, 20 ATACMs, and 864 GMLRS would be delivered before the fourth quarter of 2026. This is consistent with previous delivery timelines, https://www.taipeitimes.com/News/taiwan/archives/2026/02/09/2003852027 | https://www.govinfo.gov/content/pkg/CREC-2022-12-05/pdf/CREC-2022-12-05.pdf
2022-12-28 | Volcano Anti-Tank Mining System | 180 | Asymmetric | Does not appear in SIPRI dataset. Unspecified number of vehicle-launched anti-tank mine laying systems and related support vehicles. | Reporting from Taiwan's Liberty Times in September 2023 indicates that Taiwan received 7 Volcano systems in 2023, with 7 more expected to arrive in 2026: https://news.ltn.com.tw/amp/news/politics/paper/1602667. Reporting from Taipei Times in September 2024 indicates that half of the Volcano systems were not in fact delivered in 2023. Instead all 14 systems will be delivered in 2026: https://www.taipeitimes.com/News/taiwan/archives/2024/09/22/2003824171. The 2026 defense budget report to the LY indicates that all 14 systems will be delivered by next year, https://udn.com/news/story/10930/8974333. September 2026 press report adds details to the Volcano delivery timeline, saying that all 14 systems will be delivered in 2026, with various related equipment arriving between 2027 and 2029, https://def.ltn.com.tw/article/breakingnews/5169628. February 2026: Press report citing MND sources indicates delivery of 14 Volcano systems is scheduled to arrive "soon", https://www.taipeitimes.com/News/taiwan/archives/2026/02/09/2003852027 | https://media.defense.gov/2024/Dec/18/2003615485/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-70%20CN_0.PDF
2023-03-01 | F-16 Munitions | 619 | Munition | AGM-88B HARMs and AIM-120-C-8 AMRAAMs are most numerous missiles at 100 and 200, respectively. | These missiles might be part of a large sale of F-16 munitions that should arrive in Taiwan by the end of 2030. Some of the munitions mentioned for the 2030 delivery match with the munitions in the DSCA sale, but not all of the munitions: https://www.taiwannews.com.tw/en/news/4777553. April 2026: Raytheon awarded contract for full-rate production of AMRAAM-ER missiles for FMS customers, including Taiwan. https://www.war.gov/News/Contracts/Contract/Article/4459874/contracts-for-april-15-2026/ | https://media.defense.gov/2024/Dec/18/2003615486/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2023-09%20CN.PDF
2023-08-23 | F-16 IRST Systems | 500 | Traditional | Infrared Search and Track systems for use on F-16 aircraft. | In July 2024, Taiwanese press reported that a contract for IRST systems was signed in late June 2024 with a completion date of December 31, 2030. It is unclear at the moment if the contract termination date corresponds to final delivery of the systems or if it includes post-delivery support services: https://focustaiwan.tw/politics/202407120012. See also: https://www.janes.com/osint-insights/defence-news/air/taiwan-signs-contract-for-f-16-irst-pods. December 2025: US Air Force awards a contract to Lockheed for production of IRST pods, including 55 pods for Taiwan's Air Force. Work is expected to be completed by June 2031, https://x.com/TaiwanMonitor/status/2006808400470954306?s=20 | https://media.defense.gov/2024/Dec/18/2003615479/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2023-25%20CN.PDF
2024-02-21 | Taiwan Advanced Tactical Data Link System Upgrade | 75 | Asymmetric | Sale of GPS receivers, communication equipment, engineering and technical services, and other items to upgrade military communication systems. | In August 2024, Taiwan's e-procurement system announced the award of a contract for the Link 16 system, the major component of this arms sale, with completion date in 2026: https://www.taipeitimes.com/News/front/archives/2024/08/01/2003821602 | https://media.defense.gov/2024/Dec/18/2003615490/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-09%20CN.PDF
2024-06-18 | Switchblade 300 Loitering Missile System | 60 | Asymmetric | 720 Switchblade 300 All Up Rounds, 101 SB300 fire control systems | Taiwan press report from October 2024 indicates that Taiwan signed a LOA for both the ALTIUS and Switchblade drones in September 2024 but a contract had not been finalized yet. Taiwan's e-procurement notices for the drones showed delivery of 685 Switchblades by 2029 and 291 ALTIUS drones by 2027: https://www.taipeitimes.com/News/taiwan/archives/2024/10/30/2003826103. September 2025: Liberty Times report says that 66 Switchblades were delivered to Military Police Command in 2025. The remaining 619 Switchblade drones will be sent to the ROC Army, https://def.ltn.com.tw/article/breakingnews/5165180. | https://media.defense.gov/2024/Dec/18/2003615482/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-47%20CN.PDF
2024-10-25 | National Advanced Surface-to-Surface Air Missile System (NASAMS) | 1160 | Asymmetric | 3 NASAMS batteries, 3 AN/MPQ-64F1 Sentinel radars, 123 AMRAAM-ER Missiles, various associated radio equipment | Reporting from January 2025 said that NASAMS would be deployed in Taipei and New Taipei City https://www.taipeitimes.com/News/front/archives/2025/01/11/2003830010. Other reports from January 2025 say that Taiwan posted an E-Procurement notice for NASAMS with a completion date of 2034, however Taiwan may receive the batteries before then https://www.cna.com.tw/news/aipl/202501100287.aspx. CNA English reported on the contract announcement, specifying it was for $762 million and covered three NASAMS systems, implying that the 123 AMRAAM-ER missiles were not part of this contract announcement, https://focustaiwan.tw/politics/202502100016. April 2025 press report indicates that Taiwan should receive the first of three NASAM batteries by the end of 2025 (note: this would be a very aggressive timeline), https://www.taipeitimes.com/News/taiwan/archives/2025/04/24/2003835726. Reporting from June 2025 repeated the claim that the first NASAMS battery will arrive in Taiwan by the end of 2025 (note: this still strikes me as overly optimistic but the Taiwanese seem to believe it): https://www.taipeitimes.com/News/front/archives/2025/06/29/2003839421. Liberty Times reported that the 2026 defense budget includes a request for 9 NASAMS launchers and 339 missiles for the ROCAF, worth $3.63 billion, https://def.ltn.com.tw/article/breakingnews/5162027. October 2025, Taiwan press reports say the ROCAF will send two representatives in the United States to oversee production of NASAMS and ensure that delivery timelines are met, https://www.taiwannews.com.tw/news/6228316. October 2025, Taiwan press reports say that first tranche of NASAMS deliveries is expected to occur by the end of 2025 however it is not clear what specific equipment will be delivered in this first tranche: https://def.ltn.com.tw/article/breakingnews/5223916. February 2026: Press reports citing MND sources repeated earlier reporting that Taiwan intends to purchase 9 additional NASAMS systems. This appears to be part of another large arms sale package that is in limbo due to special procurement budget negotiations, https://www.taipeitimes.com/News/front/archives/2026/02/23/2003852725 | https://media.defense.gov/2024/Dec/18/2003615483/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-48%20CN.PDF
2024-10-25 | AN/TPS-77 and AN/TPS-78 Radar Systems | 828 | Asymmetric | Unspecified numbers of AN/TPS-77 and AN/TPS-78 radars. Both models are mobile air surveillance radars. | In January 2025, Taiwan's E-Procurement system reported a contract for L-band radars with a completion date of 2030, however, Taiwan may receive the radars before then, https://www.cna.com.tw/news/aipl/202501100287.aspx. September 2025: Reporting from Liberty Times indicates that Taiwan should receive all of its TPS radars of both types by the end of 2028. Budget request documents show a procurement of 4 TPS-77s and 5 TPS-78s. The TPS-77 has a delivery schedule of 1 each in 2026 and 2027 and 2 in 2028 while the TPS-78 has a schedule of 3 in 2027 and 2 in 2028, https://def.ltn.com.tw/article/breakingnews/5163234. | https://media.defense.gov/2024/Dec/18/2003615477/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-57%20CN.PDF
2024-12-20 | MK 75 76mm Gun Mounts | 30 | Traditional | 16 MK 75 76mm gun mounts, used on naval surface vessels | DSCA announcement says the gun mounts will be purchased from US stock then overhauled. This implies a relatively quick delivery timeline as the gun mounts are already manufactured. | https://media.defense.gov/2024/Dec/30/2003619580/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2025-01%20CN.PDF
2024-12-20 | C4 Modernization | 265 | Asymmetric | 309 MIDS JTRS radio systems; upgrade equipment for existing radios and communication systems | DSCA announcement mentions that equipment under this sale will upgrade Patriot, F-16, P-3, and HE-2K platforms. Mix of traditional and asymmetric platforms. | https://media.defense.gov/2024/Dec/30/2003619607/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2025-04%20CN%20-%20V2.PDF
2025-12-17 | ALTIUS-600M and ALTIUS-700M Systems | 1100 | Asymmetric | Unspecified numbers of two variants of ALTIUS drones. The 700M will be inert and used for training only. Includes a variety of secondary support capabilities, including launchers, spares, ground control systems, etc. | January 2026: The MND repoted that it would purchase 1,554 ALTIUS-700Ms and 478 ALTIUS-600Ms for ISR, https://def.ltn.com.tw/article/breakingnews/5314840 | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363162/taipei-economic-and-cultural-representative-office-in-the-united-states-altius
2025-12-17 | Javelin Missiles | 375 | Asymmetric | FGM-148F missiles (1,050); fly-to-buy lot acceptance missiles (10); Lightweight Command Launch Units (70) | February 2026: Amid LY deadlock over the special procurement budget, MND announced it may need to seek an extension for signing LOAs for TOWs, Javelins, and Paladins. These LOAs have a March 15 signature deadline, https://www.reuters.com/world/china/taiwan-seek-extension-arms-deals-with-us-amid-budget-stand-off-2026-02-06/. March 2026: MND officials warned that Letter of Offer and Acceptance for Javelins, as well as three other sales, would expire at end of month if not signed. LY agreed to allow signature of LOAs before special defense budget is approved. https://www.cna.com.tw/news/aipl/202603120213.aspx. April 2026: MND issued procurement contract for “anti-armor missiles,” likely meaning Javelin or TOW-2B missiles, worth US$162.75 million. https://web.pcc.gov.tw/tps/atm/AtmAwardWithoutSso/QueryAtmAwardDetail?pkAtmMain=NzExNTkzMDg=. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363124/taipei-economic-and-cultural-representative-office-in-the-united-states-javelin
2025-12-17 | TOW Missiles | 353 | Asymmetric | TOW-2B RF missiles (1,545); fly-to-buy lot acceptance missiles (14); Improved Target Acquisition System (24); mounting kits for HMMWV | February 2026: Amid LY deadlock over the special procurement budget, MND announced it may need to seek an extension for signing LOAs for TOWs, Javelins, and Paladins. These LOAs have a March 15 signature deadline, https://www.reuters.com/world/china/taiwan-seek-extension-arms-deals-with-us-amid-budget-stand-off-2026-02-06/. March 2026: MND officials warned that Letter of Offer and Acceptance for TOWs, as well as three other sales, would expire at end of month if not signed. LY agrees to allow signature of LOAs before special defense budget is approved. https://www.cna.com.tw/news/aipl/202603120213.aspx. April 2026: MND issued procurement contract for “anti-armor missiles,” likely meaning Javelin or TOW-2B missiles, worth US$162.75 million. https://web.pcc.gov.tw/tps/atm/AtmAwardWithoutSso/QueryAtmAwardDetail?pkAtmMain=NzExNTkzMDg= | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363101/taipei-economic-and-cultural-representative-office-in-the-united-states-tube-la
2025-12-17 | HIMARS (Announced December 2025) | 4050 | Asymmetric | HIMARS Launchers (82); ATACMS (420); GMLRS-U pods (756 pods; 4,536 rockets); GMLRS-AW pods (447 poids; 2,682 rockets); HMMWV vehicles (39); International Field Artillery Tactical Data Systems (45) | March 2026: MND officials warned that Letter of Offer and Acceptance for HIMARS, as well as three other sales, would expire at end of month if not signed. LY agreed to allow signature of LOAs before special defense budget is approved. https://www.cna.com.tw/news/aipl/202603120213.aspx MND officials also warned that initial payment for HIMARS would be due, but agreements with U.S. officials resulted in an extension. https://www.cna.com.tw/news/aipl/202603300094.aspx. April 2026: MND issued procurement contract for “long-range precision strike systems,” likely meaning HIMARS, worth US$3.92 billion. Lockheed Martin also received a contract for full-rate production of launchers for U.S. and FMS customers, including Taiwan. https://web.pcc.gov.tw/tps/atm/AtmAwardWithoutSso/QueryAtmAwardDetail?pkAtmMain=NzExNTkzMDM= | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363081/taipei-economic-and-cultural-representative-office-in-the-united-states-high-mo
2025-12-17 | M109A7 Paladin Howitzers | 4030 | Traditional | M109A7 Self-Propelled Howitzers (60); M992A3 Carrier Ammunition Tracked vehicles (60); M88A2 Recovery Vehicles (13); Precision Guidance Kits (4,080); M795 High Explosive Projectiles (unspecified number) | February 2026: Amid LY deadlock over the special procurement budget, MND announced it may need to seek an extension for signing LOAs for TOWs, Javelins, and Paladins. These LOAs have a March 15 signature deadline, https://www.reuters.com/world/china/taiwan-seek-extension-arms-deals-with-us-amid-budget-stand-off-2026-02-06/. March 2026: MND officials warned that Letter of Offer and Acceptance for Paladins, as well as three other sales, would expire at end of month if not signed. LY agreed to allow signature of LOAs before special defense budget is approved. https://www.cna.com.tw/news/aipl/202603120213.aspx. April 2026: MND issued procurement contract for “self-propelled artillery,” likely meaning Paladins, worth US$2.35 billion. https://web.pcc.gov.tw/tps/atm/AtmAwardWithoutSso/QueryAtmAwardDetail?pkAtmMain=NzExNTkzMDc=. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363063/taipei-economic-and-cultural-representative-office-in-the-united-states-m109a7
2025-12-17 | Tactical Mission Network | 1010 | Asymmetric | TMN includes a wide variety of software and hardware to create a tactical communications and control network that can be used to support both traditional and asymmetric equipment and operations. | January 2026: LY votes to move a special procurement budget proposed by the TPP to committee for consideration. The bill would not fund the Tactical Mission Network, but would fund almost all other FMS cases from December 2025. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363006/taipei-economic-and-cultural-representative-office-in-the-united-states-tactica
Backlog Total, March 2026 | 31719
Asymmetric Total, March 2026 | 14463
Munition Total, March 2026 | 2329
Traditional Total, March 2026 | 14927
Backlog Total, April 2026 | 29719 | -2000
Asymmetric Total, April 2026 | 14463 | No Change
Munition Total, April 2026 | 2329 | No Change
Traditional Total, April 2026 | 12927 | -2000

## Maintenance
Date of Sale | Capability Sold | Dollar Value (In Millions) | Weapon Category | Description | Administration | DSCA Sale Link
2017-06-29 | Surveillance Radar Program Support | 400 | Traditional | Operation and maintenance support for a missile and air defense early warning radar. Classified as "Traditional" due to the radar's immobility and vulnerability to attack. | Trump | https://media.defense.gov/2024/Dec/18/2003615464/-1/-1/0/TECRO_16-75_0.PDF
2018-09-24 | Foreign Military Sales Order | 330 | Traditional | Replenishment of standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Trump | https://media.defense.gov/2024/Dec/18/2003615451/-1/-1/0/TECRO_18-09_0.PDF
2019-04-15 | CONUS Based F-16 Training | 500 | Traditional | Continuation of a pilot training program and maintanence/logistics support for Taiwanese F-16s at Luke Air Force Base in Arizona. | Trump | https://media.defense.gov/2024/Dec/18/2003615452/-1/-1/0/TECRO_19-11.PDF
2020-07-09 | PAC-3 Repair and Recertification | 620 | Asymmetric | Replacement of expiring limited life components, certification testing, replenishment of missile spare parts, seeker spares pool, and other various items related to sustainment of the PAC-3. Classified as "Asymmetric" due to PAC-3s mobility and ability to shoot down aircraft. | Trump | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-13
2022-02-07 | IESP and FSP Support | 100 | Asymmetric | Equipment and services for five years to support Taiwan's participation in the Patriot International Engineering Services Program and Field Surveillance Program. Funds will sustain, maintain, and improve Taiwan's Patriot air defense systems. | Biden | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-21
2022-04-05 | Contractor Technical Assistance, Patriot | 95 | Asymmetric | Support for training, fielding, operations, and sustainment of the Patriot system. This support is supposed to improve the readiness of Taiwan's Patriot systems and ensure readiness for operations. | Biden | https://media.defense.gov/2024/Dec/18/2003615449/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-16%20CN.PDF
2022-06-08 | Ship Spare Parts | 120 | Traditional | Spare and repair parts for manned surface warships, from US Navy stocks and approved US Navy vendors. | Biden | https://media.defense.gov/2024/Dec/18/2003615450/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-22%20CN.PDF
2022-07-15 | Blanket Order Contractor Technical Support | 108 | Traditional | Spare and repair parts for tanks and other ground combat vehicles, small arms, and other capabilities. Classified as "Traditional" because tanks are a traditional capability, but the scope of this sale means it could include support for asymmetric systems. | Biden | https://media.defense.gov/2024/Dec/18/2003615492/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-31%20CN.PDF
2022-09-02 | Surveillance Radar Program Support | 665.4 | Traditional | Operation and maintenance support for a missile and air defense early warning radar. Classified as "Traditional" due to the radar's immobility and vulnerability to attack. | Biden | https://media.defense.gov/2024/Dec/18/2003615493/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-44%20CN.PDF
2022-12-06 | Aircraft Spare Parts, Standard | 330 | Traditional | Replenishment of standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Biden | https://media.defense.gov/2024/Dec/18/2003615447/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-55%20CN.PDF
2022-12-06 | Aircraft Spare Parts, Non-Standard | 98 | Traditional | Replenishment of non-standard spare parts and repair/replace of spare parts in support of Taiwan's manned fighter and transport aircraft (F-16, C-130, F-5, Indigenous Defense Fighter) | Biden | https://media.defense.gov/2024/Dec/18/2003615448/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2022-56%20CN.PDF
2023-06-29 | Foreign Military Sales Order II | 108 | Asymmetric | Spare and repair parts for wheeled vehicles, small arms, and other weapons systems. Coded as "Asymmetric" because many of Taiwan's asymmetric weapons systems (e.g. ground-based anti-ship and anti-air missiles, missile defense systems, mobile command and control systems) use wheeled vehicles, but the scope of the sale means it could include support for traditional systems. | Biden | https://media.defense.gov/2024/Dec/18/2003615487/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2023-38%20CN.PDF
2023-12-15 | C4 Life Cycle Support | 300 | Asymmetric | Life cycle support to maintain C4 capabilities (command, control, communications, and computers) associated with Taiwan's Syun An program. Spare and repair parts for C4 equipment. Also covers software development and maintenance of technical labs on US te | Biden | https://media.defense.gov/2024/Dec/18/2003615489/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2023-82%20CN.PDF
2024-06-05 | F-16 Standard Spare and Repair Parts | 220 | Traditional | Standard spare and repair parts, components, consumables and accessories for F-16 aircraft. | Biden | https://media.defense.gov/2024/Dec/18/2003615481/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-42%20CN.PDF
2024-06-05 | F-16 Non-Standard Spare and Repair Parts | 80 | Traditional | Non-standard spare and repair parts, components, consumables, and accessories for F-16 aircraft. | Biden | https://media.defense.gov/2024/Dec/18/2003615480/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-41%20CN.PDF
2024-09-16 | Return, Repair, and Reshipment of Spare Parts | 228 | Traditional | Spare parts are for "aircraft and related equipment." Also notes that spare parts will be transferred from US government stocks. | Biden | https://media.defense.gov/2024/Dec/18/2003615478/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-81%20CN.PDF
2024-11-29 | Improved Mobile Suscriber Equipment Follow-On Support | 65 | Asymmetric | Two additional years of follow-on support for the Improved Mobile Suscriber Equipment and Experimental Force system, a field communication system. | Biden | https://media.defense.gov/2024/Dec/18/2003615484/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-112%20CN.PDF
2024-11-29 | F-16 Aircraft and AESA Spare and Repair Parts | 320 | Traditional | Maintenance supplies and services for F-16 aircraft and the AESA radars used on board said aircraft. | Biden | https://media.defense.gov/2024/Dec/18/2003615491/-1/-1/0/PRESS%20RELEASE%20-%20TECRO%2024-103%20CN.PDF
2024-12-03 | Additional Equipment for CONUS F-16 Training | 7 | Traditional | Update to CONUS F-16 FMS case from 2019 that includes practice laser guided bombs and related supporting equipment. From notification, it sounds like all equipment will remain in the United States and be used by Taiwanese pilots when they come for training. | Biden | https://www.govinfo.gov/content/pkg/CREC-2024-12-03/pdf/CREC-2024-12-03.pdf
2025-11-13 | Non-Standard Spare and Repair Parts | 330 | Traditional | Non-standard spare and repair parts, components, consumables, accessories, and repair and return support for F-16, C-130, and Indigenous Defense Fighter aircraft. | Trump | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4330755/taipei-economic-and-cultural-representative-office-in-the-united-states-non-sta
2025-12-17 | Harpoon Missile Repair Follow-on Support | 91 | Asymmetric | Additional Harpoon radar seekers, spare parts, training, and other support equipment for Taiwan's growing inventory of Harpoon ASCMs. | Trump | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363138/taipei-economic-and-cultural-representative-office-in-the-united-states-harpoon
2025-12-17 | AH-1W Helicopter Spare and Repair Parts | 96 | Traditional | Spare and repair parts for AH-1W attack helicopters. | Trump | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4363047/taipei-economic-and-cultural-representative-office-in-the-united-states-ah-1w-h
Maintenance Total, April 26 | 5211
Asymmetric Maintenance Total, April 26 | 1379
Traditional Maintenance Total, April 26 | 3832
| Asymmetric, April 26 Total | Traditional, April 26 Total
Trump | 711 | 1656
Biden | 668 | 2176

## Global FMS Cases 2026
Date of Sale | Dollar Amount (Millions) | Primary Capability Sold | Secondary Capabilities Sold | Country | Region | Taiwan Backlog Overlap | Overlap Explanation | Source | Additional Sources
2026-01-06 | 1300 | Aegis Combat System Upgrade |  | Canada | North America (NATO) | Potential | Taiwan has recently received notifications of FMS cases for ship spare and repair parts, which may have some overlap. Any overlap would be relatively minor, however. | https://www.govinfo.gov/content/pkg/CREC-2026-01-06/pdf/CREC-2026-01-06.pdf
2026-01-08 | 45 | AGM-114R Hellfire Missiles (100) | AGM-114R Captive Air Test Missiles (3), M299 Hellfire Launchers (6), MHU-191/M trailers (2), BRU-14 (3) | Denmark | Europe (NATO) | No | Taiwan does use Hellfire missiles, but they are not currently in the backlog. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4373826/denmark-agm-114r-hellfire-missiles
2026-01-14 | 800 | Patriot Program Sustainment and Support |  | Kuwait | Middle East | Yes (Primary) | Taiwan has recently received notification of FMS maintenance sales to support Patriot equipment. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4379701/kuwait-patriot-program-sustainment-and-follow-on-technical-support
2026-01-14 | 110 | Very Small Aperature Terminals (VSAT) | Hubs, L-band tactical satellite services, spare parts | Iraq | Middle East | Potential | There are recent FMS cases for communications equipment that might overlap with this case, but it is not a certainty. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4379668/iraq-very-small-aperture-terminals
2026-01-15 | 1500 | Design and Construction at Callao Naval Base |  | Peru | Latin America | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4380611/peru-design-and-construction-at-callao-naval-base
2026-01-20 | 2316 | P-8A Maritime Patrol Aircraft (4); Mk 54 Lightweight Torpedoes (8) | AN/AAQ-24(V)N systems (7), anti-spoofing modules | Singapore | Indo-Pacific | No | Mk 54 conversion kits were part of the backlog recently, but those capabilities have been fully delivered. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4382957/singapore-maritime-patrol-and-reconnaissance-aircraft-p-8a-and-mk-54-lightweigh
2026-01-28 | 3160 | AIM-260 Joint Advanced Tactical Missiles (JATM) (450) | JATM Integration Test Vehicles (5); AIM-260 JATM Guided Test Vehicles (30); KGV-135A encryption devices | Australia | Indo-Pacific | No |  | http://govinfo.gov/content/pkg/CREC-2026-01-28/pdf/CREC-2026-01-28.pdf
2026-01-29 | 1700 | F-100 Frigate Mid-Life Upgrade | AEGIS Weapon Systems (5); Shipsets Digital Signal Processor (6); Mk-41 Baseline VII VLS systems (5); Next Generation Surface Search Radar (5) | Spain | Europe (NATO) | Potential | Taiwan has recently received notifications of FMS cases for ship spare and repair parts, which may have some overlap. Any overlap would be relatively minor, however. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4393093/spain-f-100-frigate-mid-life-upgrade
2026-01-30 | 9000 | PAC-3 MSE Missiles (730) | Launcher Conversion Kits; Telemetry Kits; Other support and consumable equipment | Saudi Arabia | Middle East | Yes (Primary) | Taiwan is waiting on delivery of 100 PAC-3 MSE missiles, and has discussed its intent to purchase more in the near future. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4394629/kingdom-of-saudi-arabia-patriot-advanced-capability-3-missile-segment-enhanceme
2026-01-30 | 150 | AW-119Kx Light Utility Helicopters |  | Israel | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4394591/israel-aw119kx-light-utility-helicopters
2026-01-30 | 740 | Namer APC Power Packs | Logistics Support | Israel | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4394549/israel-namer-armored-personnel-carrier-power-packs-less-transmissions-and-integ
2026-01-30 | 3800 | AH-64E Helicopters (30) | AH-64E engines, avionics, sensor equipment, other subcomponents | Israel | Middle East | Potential | Taiwan operates the AH-64E helicopter and recently has sales for aircraft spare parts but it is not clear if that includes parts for AH-64Es. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4394583/israel-ah-64e-apache-helicopters
2026-01-30 | 1980 | Joint Light Tactical Vehicle (3,250) |  | Israel | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4394563/israel-joint-light-tactical-vehicle
2026-02-03 | 3000 | F-15 Sustainment |  | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4396586/kingdom-of-saudi-arabia-f-15-sustainment
2026-02-03 | 49 | New Procruement Embedded Global Position Systems with Inertial Navigation with Multi-Mode Receivers (36) |  | Kuwait | Middle East | No |  | https://www.govinfo.gov/content/pkg/CREC-2026-02-03/pdf/CREC-2026-02-03.pdf
2026-02-05 | 90 | VACIS XPL Passenger Vehicle Scanning Systems |  | Iraq | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4398638/iraq-contracted-logistical-services-for-vacis-xpl-passenger-vehicle-scanning-sy
2026-02-06 | 185 | Class IX Spare Parts |  | Ukraine | Europe (Non-NATO) | Potential | There are multile recent FMS cases for spare parts for various US-made vehicles that Taiwan operates. There may be some overlap, but it is impossible to determine given available information. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4399552/ukraine-class-ix-spare-parts
2026-02-26 | 280 | Ku Band Multifunction Radio Frequency System Radars |  | Jordan | Middle East | No |  | https://www.state.gov/jordan-ku-band-multi-function-radio-frequency-system-kumrfs-radars/
2026-03-06 | 152 | BLU-110A/B 1,000-lb bomb bodies (12,000) |  | Israel | Middle East | No |  | https://www.state.gov/israel-munitions-and-munitions-support/
2026-03-10 | 930 | HIMARS (20), GMLRS-Unitary Pods (35), GMLRS-Alternative Warhead Pods (35), GMLRS-ER Unitary Pods (35), ATACMS (20), IFATDS (24) |  | Sweden | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of 82 HIMARS systems, GMLRS pods, ATACMS, and IFATDS | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/03/sweden-m142-high-mobility-artillery-rocket-systems/
2026-03-19 | 1220 | AIM-120C AMRAAMs (400) | AIM-120C-8 Guidance Sections (8) | United Arab Emirates | Middle East | No |  | https://www.state.gov/united-arab-emirates-advanced-medium-range-air-to-air-missiles-amraams/
2026-03-19 | 644 | GBU-39/B Small Diameter Bombs (1,500) | KMU-556 JDAM Guidance Sets (900), KMU-557 JDAM Guidance Sets (300), GBU-39/B inert practice bombs (3) | United Arab Emirates | Middle East | No |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/03/united-arab-emirates-f-16-munitions-and-upgrades/
2026-03-19 | 4500 | Long-Range Discrimination Radar integrated with Terminal High Altitude Area Defense (THAAD) | Sentinel A4 Uplinkers (12), THAAD C3 Fire Control and Communications (TFCC) Tactical Operations Stations (2), THAAD C3 TFCC Launch and Control Stations (2) | United Arab Emirates | Middle East | No |  | https://www.state.gov/united-arab-emirates-long-range-discrimination-radar-with-terminal-high-altitude-area-defense-integration/
2026-03-19 | 70.5 | Aircraft Repair, Return, and Spares |  | Jordan | Middle East | Potential |  | https://www.state.gov/government-of-jordan-aircraft-repair-return-and-spares/
2026-03-19 | 8000 | Lower Tier Air and Missile Defense Sensor (LTAMDS) Radars (8) | Large Tactical Power Systems (5), Frequency Converters (8) | Kuwait | Middle East | Potential | Media has reported that a future arms sale to Taiwan may include LTAMDS radars | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/03/kuwait-lower-tier-air-and-missile-defense-sensor-radars/
2026-03-19 | 2100 | Fixed Site-Low, Slow, Small Unmanned Aircraft Integrated Defeat Systems (FS-LIDS) Systems (10), incl. Coyote Block 2 All Up Rounds (240) |  | United Arab Emirates | Middle East | No |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/03/united-arab-emirates-fixed-site-low-slow-small-unmanned-aircraft-integrated-defeat-system/
2026-03-20 | 1000 | Submarine Combat and Weapons Systems, Technical Support, US and UK Embedded Personnel, and Associated Training |  | United Kingdom | Europe (NATO) | No |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/03/united-kingdom-submarine-combat-and-weapon-systems-technical-support-u-s-and-uk-embedded-personnel-and-associated-training/
2026-03-25 | 200 | ARC-210 RT-2036C Secure Radios and KY-100M Communication Security Devices |  | South Korea | Indo-Pacific | No |  | https://www.state.gov/republic-of-korea-arc-210-rt-2036c-secure-radios-and-ky-100m-communication-security-devices/
2026-03-25 | 340 | Hyper-Velocity Gliding Projectile (HVGP) Program Support |  | Japan | Indo-Pacific | No |  | https://www.state.gov/japan-hyper-velocity-gliding-projectile-hvgp-program-support/
2026-03-25 | 156 | AN/PRC-163 Radios, AN/PRC-167 Radios; AN/PRC-160 Radios; KIK-11 Tactical Key Loaders, and Associated Equipment |  | Belgium | Europe (NATO) | No |  | https://www.state.gov/belgium-communications-equipment/
2026-04-01 | 83 | Guided Multiple Launch Rocket System-Alternative Warhead Pods (45) |  | Singapore | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of GMLRS-AW pods | https://www.state.gov/singapore-guided-multiple-launch-rocket-system-alternative-warhead/
2026-04-17 | 11900 | AEGIS-based Integrated Combat System (ICS) MK 6 MOD X computing infrastructures (8); AN/SPY-6(V)1 AESA S-Band Radars (8); MK 41 Baseline VII Vertical Launch Systems (8) | Cooperative Engagement Capability (8); Global Positioning System-based Positioning Navigation and Timing Service (8); Command and Control Processors (9); Multifunctional Information Distribution Systems on Ship Modernization systems (10); MK 45 Gun Mounts (9); AN/SLQ-32(V)6 Electronic Warfare Systems (3), AN/SPQ-9B radar systems (8), AN/WSN-12 Inertial Navigation Systems (8) | Germany | Europe (NATO) | No |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/04/germany-integrated-combat-system-supporting-equipment-and-support/
2026-04-22 | 200 | AGM-114R2 Hellfire Missiles (530) |  | Netherlands | Europe (NATO) | No |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/04/the-netherlands-hellfire-missiles/
2026-04-22 | 214 | AIM-9X Block II Sidewinder Missiles (152) | AIM-9X Block II Tactical Guidance Units (8); AIM-9X Block II Captive Air Training Missiles (6) | Lithuania | Europe (NATO) | Yes (Primary) |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/04/lithuania-aim-9x-sidewinder-block-ii-missiles/
2026-04-27 | 95 | Border Security Project Phase III |  | Tunisia | Middle East | No |  | https://www.state.gov/releases/bureau-of-political-military-affairs/2026/04/tunisia-border-security-project-phase-iii/

## Global FMS Cases 2025
Date of Sale | Dollar Amount (Millions) | Primary Capability Sold | Secondary Capabilities Sold | Country | Region | Taiwan Backlog Overlap | Overlap Explanation | Source | Additional Sources
2025-01-02 | 3640 | AIM-120C-8 and AIM-120D-3 Missiles (1,200) | AIM-120D-3 Guidance Sections (20); AIM-120C-8 Guidance Sections (4) | Japan | Indo-Pacific | Yes (Primary) | Taiwan is waiting for delivery of two variants of AMRAAM missiles from a sale of F-16 munitions and the sale of NASAM batteries. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-120d-3-and-aim-120c-8-advanced-medium-range-air-air-missiles
2025-01-03 | 79 | MK 54 Mod 0 Lightweight Torpedoes (20) | Spare parts; recoverable exercise torpedoes | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-mk-54-mod-0-lightweight-torpedoes
2025-01-13 | 100 | Bell 412 Helicopters |  | Zamiba | Africa | No |  | https://www.dsca.mil/press-media/major-arms-sales/republic-zambia-bell-412-enhanced-performance-exportable-medium-lift
2025-01-15 | 39 | JASSM-ER Missiles (16) | AGM-158 JASSM Dummy Air Training Missiles; anti-jam GPS receivers; spare parts | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-joint-air-surface-standoff-missiles-extended-range
2025-01-08 | 900 | SM-6 Block 1 Missiles (150) | Mk-21 VLS canisters; handling equipment; spare parts | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-standard-missile-6-sm-6-block-i-missiles
2025-02-04 | 625 | Component Based Total Ship System, 21st Century (COMBATSS-21) (4) | Air and Surface surveillance radars; electronic warfare systems; fire control radar; 76mm gun upgrades | Egypt | Middle East | Yes (Secondary) | Taiwan is waiting on delivery of 76mm gun mounts. 76mm gun upgrades are part of this arms sale. | https://www.dsca.mil/press-media/major-arms-sales/egypt-fast-missile-craft-modernization
2025-02-04 | 304 | AN/TPS-78 Long Range Radar Systems |  | Egypt | Middle East | Yes (Primary) | Taiwan purchased AN/TPS-78 radars as part of a December 2024 FMS case. | https://www.dsca.mil/press-media/major-arms-sales/egypt-antps-78-long-range-radar
2025-02-06 | 1000 | Design and Construction Services for naval bases |  | Kuwait | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kuwait-design-and-construction-services
2025-02-07 | 6750 | GBU-39B Small Diameter Bombs (2,166); Mk 82 500lb bombs (2,800) | Tens of Thousands of JDAM Guidance Kits | Israel | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/israel-munitions-guidance-kits-fuzes-and-munitions-support
2025-02-07 | 660 | AGM-114 Hellfire Missiles (3,000) |  | Israel | Middle East | No | NOTE: This FMS notification includes an estimate for deliveries to begin in 2028. | https://www.dsca.mil/press-media/major-arms-sales/israel-agm-114-hellfire-missiles
2025-02-18 | 84 | GBU-39B Small Diameter Bomb (400) | Inert Practice Bombs with fuze (2) | Romania | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/romania-gbu-39b-small-diameter-bombs
2025-02-28 | 295 | D9R and D9T Bulldozers |  | Israel | Middle East | No | NOTE: This FMS notification includes an estimate for deliveries to begin in 2027. | https://www.dsca.mil/press-media/major-arms-sales/israel-caterpillar-d9-bulldozers
2025-02-28 | 676 | Mk 83 1,000lb bombs (201); BLU-110A/B 1,000lb bombs (4,799) | Various JDAM Guidance Kits (5,000 total) | Israel | Middle East | No | NOTE: This FMS notification includes an estimate for deliveries to begin in 2028. | https://www.dsca.mil/press-media/major-arms-sales/israel-munitions-guidance-kits-and-munitions-support
2025-02-28 | 2040 | Mk 84 or BLU-117 Bombs (35,539) | I-2000 Penetrator Warheads (2,000) | Israel | Middle East | No | NOTE: This FMS notification includes an estimate for deliveries to begin in 2026. | https://www.dsca.mil/press-media/major-arms-sales/israel-munitions-and-munitions-support
2025-03-10 | 91 | GMLRS-AW Rounds (54) |  | Australia | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of GMLRS rounds as part of its purchases of HIMARS. It is not clear if Taiwan purchased AW rounds, but AW rounds use the same rocket motor and guidance system as standard GMLRS rockets | https://www.dsca.mil/press-media/major-arms-sales/australia-guided-multiple-launch-rocket-system-alternate-warhead
2025-03-10 | 200 | Hyper Velocity Gliding Projectiles Capability Support |  | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-hyper-velocity-gliding-projectiles-capability-support
2025-03-18 | 165 | MJU-61 decoy flares; MJU-66 flare countermeasures; MJU-76 flare countermeasures | RR-198A/L chaff cartridges; CCU-145/A Impulse cartridges | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-countermeasures-chaff-and-impulse-cartridges
2025-03-20 | 100 | Advanced Precision Kill Weapon System APKWS (2,000) |  | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-advanced-precision-kill-weapon-systems
2025-03-24 | 509 | AIM-120C-8 AMRAAM (120) | AIM-120C-8 Guidance Sections (10); spare AIM-120 control sections and containers | Belgium | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of AIM-120 missiles as part of a sale of F-16 munitions and NASAMS batteries. | https://www.govinfo.gov/content/pkg/CREC-2025-03-24/pdf/CREC-2025-03-24.pdf
2025-03-24 | 49 | AIM-120D-3 AMRAAM (4) | AIM-120D-3 Guidance Sections (2); AIM-120D-3 Integrated Test Vehicles (2) | Italy | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of AIM-120 missiles as part of a sale of F-16 munitions and NASAMS batteries. | https://www.govinfo.gov/content/pkg/CREC-2025-03-24/pdf/CREC-2025-03-24.pdf
2025-03-24 | 520 | Design and Construction Services for F-15QA related facilities |  | Qatar | Middle East | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-03-24/pdf/CREC-2025-03-24.pdf
2025-03-26 | 1960 | MQ-9B UAVs (8) | KMU-572 JDAM tail kits (200); BLU-111 general purpose bombs (300); MXU-650 air foil groups for Paveway II GBU-12 (100); MAU-169 Computer Control Groups for Paveway II GBU-12 (100); other munitions, radars, and components | Qatar | Middle East | Yes (Primary) | Taiwan is waiting for delivery of 4 MQ-9B aircraft and 2 ground control stations. | https://www.dsca.mil/press-media/major-arms-sales/qatar-mq-9b-remotely-piloted-aircraft
2025-04-01 | 64 | M4A1 Rifles | Magazines, technical manuals, training and support | Ecuador | Latin America | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4142306/ecuador-m4a1-rifles-and-support
2025-04-01 | 5580 | F-16 C Block 70/72 Aircraft (16); F-16 D Block 70/72 Aircraft (4) | Aircraft Engines; avionics; radar systems; mission computers; AIM-120C-8 AMRAAM Missiles (112); AIM-9X Block II Missiles (40); GBU-39B Small Diameter Bombs (36); Viper Shield Electronic Warfare System | Philippines | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of both F-16 Block 70/72 aircraft (first one rolled off production line in March 2025). Taiwan is also waiting on delivery of AIM-120 and AIM-9X missiles. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4142323/philippines-f-16-aircraft
2025-04-03 | 400 | Upgrade and Recertification of PATRIOT Missiles (PAC-2 GEM and GEM-T) |  | Kuwait | Middle East | No | Taiwan is waiting on delivery of 100 PAC-3 MSE interceptors. Any common subystems between those and PAC-2 GEM/GEM-T would be overlapping. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4144885/kuwait-upgrade-and-recertification-of-patriot-missiles
2025-04-09 | 1040 | AIM-120C-8 AMRAAM Missiles (200); AIM-120D-3 AMRAAM Missiles (200) | Containers; support equipment; spare parts; missile software; technical assistance | Australia | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of AIM-120 missiles as part of a sale of F-16 munitions and NASAMS batteries. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4150603/australia-aim-120c-and-aim-120d-advanced-medium-range-air-to-air-missiles
2025-04-09 | 13 | MIDS JTRS V5 Systems (35) |  | Romania | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-04-09/pdf/CREC-2025-04-09.pdf
2025-04-14 | 180 | Eitan Powerpack Engines (Armored Fighting Vehicle) |  | Israel | Middle East | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4154118/israel-eitan-powerpack-engines
2025-04-15 | 120 | TH-73A Training Helicopters |  | Philippines | Indo-Pacific | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4155316/philippines-th-73a-training-helicopters-and-support
2025-04-15 | 825 | FIM-92K Stinger Missiles (600) |  | Morocco | Middle East | Yes (Primary) | Taiwan is waiting on delivery of Stinger missiles. It also has announced its intention to purchase more than 2,000 Stingers in the near future but there was no CN for such a plus up as of April 2025 | https://www.dsca.mil/Congressional-Notification-Archive/Article/4155284/kingdom-of-morocco-fim-92k-stinger-block-i-missiles
2025-04-23 | 46 | Javelin Lightweight Command Launch Units (36) |  | Ireland | Europe (Non-NATO) | No | Earlier versions of the backlog dataset included Javelins but Taiwan has received all of these systems. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4164095/ireland-fgm-148-javelin-missiles-and-lightweight-command-launch-units
2025-04-25 | 2190 | Tomahawk Block V Missiles (163); Tomahawk Block IV Missiles (12) | Tactical Tomahawk Weapons Control Systems (10); Tomahawk Block IV Telemetry Missiles (2) | Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4166632/the-netherlands-tomahawk-land-attack-missiles
2025-04-28 | 3 | Javelin Lightweight Command Launch Units (15) |  | Brazil | Latin America | No | Earlier versions of the backlog dataset included Javelins but Taiwan has received all of these systems. | https://www.govinfo.gov/content/pkg/CREC-2025-04-28/pdf/CREC-2025-04-28.pdf
2025-04-28 | 625 | AIM-120D-3 AMRAAM (240) | AMRAAM Guidance Sections (8) | Finland | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.govinfo.gov/content/pkg/CREC-2025-04-28/pdf/CREC-2025-04-28.pdf
2025-04-28 | 630 | OT-228/U Common Infrared Countermeasures (47) | EAGLE-M Aviation Navigation System (144) | Germany | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-04-28/pdf/CREC-2025-04-28.pdf
2025-04-28 | 280 | Patriot Air Defense System | AN/MPQ-65 Radar Set (1); AN/MSQ-132 Engagement Control Station (1); M903 Launchers (2); Electrical Power Plant (1) | Romania | Europe (NATO) | No | Taiwan operates the Patriot system and PAC-3 MSE interceptors are currently in the backlog. However, none of theequipment described in this arms sale is currently in the backlog. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4167631/romania-patriot-air-defense-system
2025-04-28 | 8 | Embedded Global Positioning System (44) | For CH-47 Helicopters | South Korea | Indo-Pacific | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-04-28/pdf/CREC-2025-04-28.pdf
2025-04-28 | 21 | International Field Artillery Tactical Data System (IFATDS) (18) | For HIMARS launcher sale | Lithuania | Europe (NATO) | Unclear | Taiwan is waiting on delivery of HIMARS launchers which are presumably equipped with this subsystem. However it is not certain that they are from the CN language. | https://www.govinfo.gov/content/pkg/CREC-2025-04-28/pdf/CREC-2025-04-28.pdf
2025-04-29 | 1330 | AIM-120D3 AMRAAM (400) | AMRAAM Guidance Sections (16); Instrumented Test Vehicle (1) | Poland | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4168673/poland-aim-120d-advanced-medium-range-air-to-air-missiles
2025-04-30 | 425 | Patriot Post-Deployment Build 8.1 Upgrades |  | Kuwait | Middle East | No | Taiwan operates the Patriot system, but it is not currently waiting on delivery of this particular Patriot equipment. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4170479/kuwait-patriot-post-deployment-build-81
2025-04-30 | 131 | Indo-Pacific Maritime Domain Awareness Equipment |  | India | Indo-Pacific | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4170460/india-indo-pacific-maritime-domain-awareness
2025-05-02 | 3500 | AIM-120C-8 AMRAAM (1,000) | AIM-120C-8 AMRAAM Guidance Sections (50) | Saudi Arabia | Middle East | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4173146/kingdom-of-saudi-arabia-aim-120c-8-advanced-medium-range-air-to-air-missiles
2025-05-02 | 310 | F-16 Training and Sustainment |  | Ukraine | Europe (Non-NATO) | Yes (Primary) | Taiwan regularly purchases F-16 training and sustainment items from the US via the FMS process. However, this dataset does not track delivery progress of these items and services. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4173182/ukraine-f-16-training-and-sustainment
2025-05-02 | 371 | AIM-9X Block II Missiles (300) | AIM-9X Block II special air training missiles (2); captive air training missiles (24); tactical guidance units (20) | Norway | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of an AIM-9X sale. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4173194/norway-aim-9x-block-ii-tactical-missiles
2025-05-05 | 181 | Communications Equipment |  | Czech Republic | Europe (NATO) | Potential | There are two Taiwan FMS cases for communications equipment currently in the backlog. However, a detailed breakdown of specific capabilities is not included. It is possible that there is overlap, but it cannot be proven with current information. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4174285/czech-republic-communications-equipment
2025-05-12 | 1320 | CH-47 Helicopters (6) | Various CH-47 equipment (engines, avionics, radios, subsystems, etc.) | UAE | Middle East | No | Taiwan operates the Chinook but none are currently in the backlog. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4182033/united-arab-emirates-ch-47f-chinook-helicopters
2025-05-12 | 130 | F-16 Sustainment |  | UAE | Middle East | Yes (Primary) | Taiwan regularly purchases F-16 training and sustainment items from the US via the FMS process. However, this dataset does not track delivery progress of these items and services. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4182037/united-arab-emirates-f-16-sustainment
2025-05-13 | 300 | FMSO case, CLSSA for AH-64, UH-60, and CH-47 helicopters |  | UAE | Middle East | No | Taiwan operates all of these helicopters but maintenance sales like this one are not included in the backlog. | https://www.govinfo.gov/content/pkg/CREC-2025-05-13/pdf/CREC-2025-05-13.pdf
2025-05-14 | 79 | AIM-9X Block II Missiles (60) | AIM-9X Block II tactical guidance units (11) | Turkey | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of an AIM-9X sale. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4186475/trkiye-aim-9x-sidewinder-block-ii-missiles
2025-05-14 | 225 | AIM-120C-8 AMRAAM Missiles (53) | Guidance Sections (6) | Turkey | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4186456/trkiye-aim-120c-8-advanced-medium-range-air-to-air-missiles
2025-05-14 | 500 | M403 Extended Range Guided Multiple Launch Rocket System (ER-GMLRS) Alternative Warhead Pods (25) | M404 ER-GMLRS Unitary Pods (25) | Norway | Europe (NATO) | Yes (Primary) | GMLRS and ATACMS are subcomponents of the two HIMARS sales, which should complete delivery by the end of 2026. | https://www.govinfo.gov/content/pkg/CREC-2025-05-14/pdf/CREC-2025-05-14.pdf
2025-05-19 | 1006 | PAC-3 MSE Missiles (107) | PAC-3 MSE Test Missiles (5) | South Korea | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of 100 PAC-3 MSE interceptors. | https://www.govinfo.gov/content/pkg/CREC-2025-05-19/pdf/CREC-2025-05-19.pdf
2025-05-19 | 5800 | Patriot GEM-T Missiles (788) |  | Poland | Europe (NATO) | Yes (Potential) | Taiwan is waiting on delivery of 100 PAC-3 MSE interceptors. Any common subystems between those and GEM-T would be overlapping. | https://www.govinfo.gov/content/pkg/CREC-2025-05-19/pdf/CREC-2025-05-19.pdf
2025-05-19 | 200 | Sustainment of US Army Supplied Systems |  | Ukraine | Europe (Non-NATO) | Unclear | Taiwan fields multiple US Army systems in its armed forces, it is therefore possible that it would purchase sustainment items via FMS. Additionally, the CN for this sale specifies that Ukraine will use FMF to fund the purchase. | https://www.govinfo.gov/content/pkg/CREC-2025-05-19/pdf/CREC-2025-05-19.pdf
2025-05-20 | 100 | AW-199Kx Helicopters |  | Bosnia and Herzegovina | Europe (Non-NATO) | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4192556/bosnia-and-herzegovina-aw-119kx-helicopters
2025-05-21 | 180 | GBU-39/B Small Diameter Bombs (1,400) | GBU-39(T-1)/B Inert Practice Bombs with Fuzes (4) | Poland | Europe (NATO) | No |  | https://www.dsca.mil/Congressional-Notification-Archive/Article/4194147/poland-gbu-39b-small-diameter-bombs
2025-05-22 | 296 | FGM-148F Javelin Missiles (800) | Javelin Lightweight Command Launch Units (72) | Estonia | Europe (NATO) | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/Congressional-Notification-Archive/Article/4195631/estonia-javelin-missiles
2025-06-04 | 325 | M1A2 Abrams Sustainment Support |  | Kuwait | Middle East | Yes (Primary) | Taiwan is receiving Abrams tanks between late 2024 and 2026. While its tanks are of a slightly different variant, they would share many common systems that would need to be sustained. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4206289/kuwait-m1a2-abrams-main-battle-tank-system-sustainment-support
2025-06-05 | 16 | Various Communication and Navigation Systems for Black Hawk Helicopters |  | Sweden | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-06-05/pdf/CREC-2025-06-05.pdf
2025-06-10 | 149 | JDAM Kits for GBU-38 (16); AN/APY-8 Lynx Synthetic Aperture Radars (4) |  | Canada | North America (NATO) | Potential | The systems in this arms sale support Canada's MQ-9B capabilities. Taiwan is waiting on delivery of MQ-9Bs which may or may not include similar component systems. | https://www.govinfo.gov/content/pkg/CREC-2025-06-10/pdf/CREC-2025-06-10.pdf
2025-06-10 | 1610 | CLS Services for RQ-4 Global Hawk Drones |  | Japan | Indo-Pacific | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-06-10/pdf/CREC-2025-06-10.pdf
2025-06-12 | 215 | AGM-179A Joint Air-to-Ground Missiles (296) | Captive Air Training Missiles; various forms of technical assistance; missile handling training | The Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4215271/the-netherlands-joint-air-to-ground-missiles
2025-06-16 | 211 | AIM-120D-3 AMRAAM (30); AIM-120C-8 AMRAAM (40) | Guidance Sectionsl Control Sections and Spares | Italy | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4217573/italy-advanced-medium-range-air-to-air-missiles
2025-06-16 | 2000 | F/A-18F and EA-18G Sustainment Support | Global Lightning JTT-X Receivers (60); Advanced Electronic Warfare Systems (40); Next Generation Electronic Attack Units (24) | Australia | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4217508/australia-fa-18f-and-ea-18g-sustainment-support
2025-06-30 | 510 | JDAM Kits for BLU-109 (3,845) and MK 82 (3,280) |  | Israel | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4230375/israel-munitions-guidance-kits-and-munitions-support
2025-07-11 | 100 | A-29 Super Tucano Aircraft Sustainment |  | Lebanon | Middle East | No | Modification of an earlier FMS case that was below the notification threshold. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4241763/lebanon-a-29-super-tucano-aircraft-sustainment
2025-07-11 | 2600 | HH-60W Helicopters (9) | Associated engines (22); GPS systems (21); various avionics and missile warning systems | Norway | Europe (NATO) | No | Taiwan operates the UH-60M helicopter, but not the HH-60W variant. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4241742/norway-hh-60w-helicopters
2025-07-17 | 100 | PAC-3 Missiles |  | Kuwait | Middle East | No | This notifies Congress of cost increases to an ongoing FMS case for Patriot interceptors. There are no new capabilities being added to the sale. | https://www.govinfo.gov/content/pkg/CREC-2025-07-17/pdf/CREC-2025-07-17.pdf
2025-07-17 | 142 | Guidance Kits for multiple types of JDAMs and other guided aircraft bombs |  | NATO Support and Procurement Agency | Europe (NATO) | No | Modification of an earlier FMS case. | https://www.govinfo.gov/content/pkg/CREC-2025-07-17/pdf/CREC-2025-07-17.pdf
2025-07-17 | 15 | GBU-39/B Small Diameter Bombs (50); BLU-109 bombs (162) |  | NATO Support and Procurement Agency | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-07-17/pdf/CREC-2025-07-17.pdf
2025-07-17 | 2 | Guardian Laser Transmitter Assembly for Large Aircraft Infrared Countermeasures system (1) |  | New Zealand | Indo-Pacific | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-07-17/pdf/CREC-2025-07-17.pdf
2025-07-21 | 620 | Naval Strike Missile Coastal Defense System (1) | Link-16 MIDS-JTRS; NSMs (unspecified number) | Bulgaria | Europe (NATO) | Potential | Link-16 systems are likely a component of at least one if not two arms sales to Taiwan, but those sales do not specify their subsystems. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4250841/bulgaria-naval-strike-missile-coastal-defense-system
2025-07-23 | 172 | HAWK Phase III Missile System Sustainment |  | Ukraine | Europe (Non-NATO) | No | Taiwan recently retired all of its HAWK missile systems. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4253428/ukraine-hawk-phase-iii-missile-system-and-sustainment
2025-07-23 | 150 | Bradley IFV Maintenance, Repair, and Overhaul |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4253473/ukraine-bradley-infantry-fighting-vehicles-and-maintenance-repair-and-overhaul
2025-07-24 | 180 | Air Defense Sustainment |  | Ukraine | Europe (Non-NATO) | Potential | Ukraine and Taiwan operate some similar air defense capabilities. It is possible that this FMS case to Ukraine would include common spare parts, but impossible to say for sure from the notification. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4254530/ukraine-air-defense-sustainment
2025-07-24 | 150 | M109 Self-Propelled Howitzer Maintenance, Repair, and Overhaul |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4254520/ukraine-m109-self-propelled-howitzer-maintenance-repair-and-overhaul-capability
2025-07-24 | 4670 | NASAMS (4) | AN/MPQ-64F1 Sentinel radars (4); AMRAAM-ER Missiles (100); AIM-120-C8 Missiles (100); AIM-9X Block II Missiles (600) | Egypt | Middle East | Yes (Primary) | Taiwan is waiting for delivery of 3 NASAMS batteries and associated munitions. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4254503/egypt-national-advanced-surface-to-air-missile-system
2025-08-05 | 104 | M777 Howitzer Equipment, Repair Services and Sustainment |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4266194/ukraine-equipment-repair-services-and-sustainment-support-for-m777-howitzers
2025-08-05 | 99 | Transportation and Consolidation Services |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4266161/ukraine-transportation-and-consolidation-services
2025-08-06 | 404 | MC-55A Baseline 2 SIGINT/ELINT Gulfstream Aircraft Upgrades |  | Australia | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4267141/australia-mc-55a-baseline-2-upgrade
2025-08-08 | 160 | Joint Light Tactical Vehicle (60) | JLTV Cargo Trailers (9) | Canada | North America (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4270288/canada-joint-light-tactical-vehicles
2025-08-13 | 346 | Mark 82 500-lb Bombs (1,002) and Advanced Precision Kill Weapon System II (APKWS II) All-Up Rounds (5,000) | JDAM Kits for Paveway II GBU-12 Bombs (1,002), 250-lb Paveway II GBU-58 Bombs (515), Computer Control Groups for Paveway II GBU-12/GBU-58 Bombs (1,517), Joint Programmable Fuzes (1,002) | Nigeria | Africa | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4273754/nigeria-munitions-precision-bombs-and-precision-rockets
2025-08-14 | 500 | HIMARS (4) | International Field Artillery Tactical Data Systems (3), M28A2 Low Cost Reduced Range Practice Rocket Pods, HMMWV Fire Direction Centers, resupply vehicles, driver vision enhancer systems, and advanced GPS receivers | Bahrain | Middle East | Yes (Primary) | Taiwan is waiting for delivery of 18 of 29 HIMARS ordered; already received 11. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4274789/bahrain-m142-high-mobility-artillery-rocket-system
2025-08-19 | 97 | Javelin Lightweight Command Launch Units (161) |  | Australia | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4279065/australia-javelin-lightweight-command-launch-unit
2025-08-26 | 861 | C-17 Aircraft Contractor Logistical Support |  | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4285993/united-kingdom-c-17-globemaster-iii-aircraft-sustainment-support
2025-08-26 | 1850 | F-35 Sustainment |  | Poland | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4285956/poland-f-35-sustainment
2025-08-27 | 104 | AIM-9X Block II Missiles (96) |  | NATO Support and Procurement Agency | Europe (NATO) | Yes (Primary) | Taiwan waiting on delivery of 100 AIM-9X Block II missiles. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4287772/nato-support-and-procurement-agency-aim-9x-sidewinder-missiles
2025-08-28 | 825 | Extended Range Attack Munition (ERAM) Missiles (3,350) | Embedded GPS/INS (EGI) with Selective Availability Anti-Spoofing Module (SAASM) (3,350) | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4289280/ukraine-air-delivered-munitions
2025-08-29 | 179 | Patriot Sustainment |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4290514/ukraine-patriot-air-defense-system-sustainment
2025-08-29 | 150 | Satellite Communications Services |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4290506/ukraine-satellite-communications-services
2025-08-29 | 8500 | Patriot GEM-T Missiles (36), Patriot PAC-3 MSE Missiles (20), Engagement Control Stations and Centers (2), and Launching Stations (6) | AN/MPQ-65 Radar Set (2); IBCS Software LINKs (6), IBCS Engagement Operations Centers and Integrated Collaborative Environment (2), IBCS integrated fire control network relays (6), Electrical Power Plants III (2) | Denmark | Europe (NATO) | Yes (Primary) | Taiwan waiting on delivery of 100 PAC-3 MSE interceptors. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4290498/denmark-integrated-battle-command-system-enabled-patriot
2025-09-02 | 120 | AIM-9X Block II Missiles (100) | AIM-9X Captive Air Training Missiles (31) | Italy | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of AIM-9X missiles. | https://www.govinfo.gov/content/pkg/CREC-2025-09-02/pdf/CREC-2025-09-02.pdf
2025-09-10 | 1070 | AIM-120D-3 AMRAAM (405) | AIM-120D-3 Guidance Section (8) | Finland | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4299369/finland-aim-120d-3-advanced-medium-range-air-to-air-missiles
2025-09-11 | 790 | AIM-120D AMRAAM (244) | AIM-120D-3 Guidance Sections (4); Test Vehicle (1) | United Kingdom | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.govinfo.gov/content/pkg/CREC-2025-09-11/pdf/CREC-2025-09-11.pdf
2025-09-15 | 3420 | F-16C Block 70 Aircraft (10) and F-16D Block 70 Aircraft (2) | F110-GE-129 Engines (14), Improved Programmable Display Generators (14), AIM-120C-8 AMRAAMs (12), LAU-129 guided missile launchers (52), M61A1 anti-aircraft guns (12), Embedded Global Positioning System Inertial Navigation Systems (14), AN/APG-83 AESA Scalable Agile Beam Radars (14), Modular Mission Computers 7000AH (14), AIM-9X Sidewinder II missiles (12), Sidewinder tactical guidance units (2), Sidewinder Captive Air Training Missiles (2), Sidewinder CATM guidance units (1), Multifunctional Information Distribution System-Joint Tactical Radio Systems (14) | Peru | Latin America | Yes (Primary) | Taiwan waiting on delivery of the same F-16 model (C/D Block 70), which is scheduled to complete in 2026. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4304541/peru-f-16-aircraft
2025-09-15 | 113 | GBU-39/B Small Diameter Bombs Increment I (816) |  | Norway | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4304040/norway-gbu-39b-small-diameter-bomb-increment-i
2025-09-15 | 568 | AIM-9X Block II Missiles (320), AIM-9X Block II+ Missiles (258) | AIM-9X Block II Missile Guidance Units (50), AIM-9X Block II+ Missile Guidance Units (30) | Belgium | Europe (NATO) | Yes (Primary) | Taiwan waiting on delivery of 100 AIM-9X Block II missiles. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4304022/belgium-aim-9x-sidewinder-missiles
2025-09-16 | 140 | Common Infrared Countermeasure Systems (33) | Subsystems for AH-64E helicopters | Australia | Indo-Pacific | No | Taiwan operates the AH-64, but it does not currently have these subsystems in the backlog. | https://www.govinfo.gov/content/pkg/CREC-2025-09-16/pdf/CREC-2025-09-16.pdf
2025-09-16 | 570 | AIM-120C-8 AMRAAM (232) | AIM-120C-8 Guidance Sections (8) | Netherlands | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4305375/the-netherlands-aim-120c-8-advanced-medium-range-air-to-air-missiles
2025-09-16 | 7 | Communications Systems for UH-60M Helicopters |  | Austria | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-09-16/pdf/CREC-2025-09-16.pdf
2025-09-16 | 404 | AAV-7 Amphibious Assault Vehicles (44, various variants) | .50 and 7.62mm machine guns for vehicles | Romania | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-09-16/pdf/CREC-2025-09-16.pdf
2025-09-17 | 162 | MK 54 Mod 0 Lightweight Torpedoes (50) |  | Norway | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4306771/norway-mk-54-mod-0-lightweight-torpedoes
2025-09-18 | 200 | Bell 412 Helicopter Logistics Support |  | Iraq | Middle East | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-09-18/pdf/CREC-2025-09-18.pdf
2025-09-18 | 611 | Aircraft Spare Parts for F-16s |  | Poland | Europe (NATO) | Yes (Potential) | There have been several FMS cases for aircraft spare parts to Taiwan in recent years, including for F-16s. Our dataset does not track the delivery status of these parts, but there is likely some overlap. | https://www.govinfo.gov/content/pkg/CREC-2025-09-18/pdf/CREC-2025-09-18.pdf
2025-09-18 | 780 | FGM-148F Javelin Missiles (2,506) | Javelin Lightweight Command Launch Units (253) | Poland | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4307858/poland-javelin-missile-systems
2025-09-25 | 1230 | AIM-120D-3 AMRAAM (400) | AIM-120D-3 Guidance Sections (12), AIM-120 AMRAAM Integrated Test Vehicle (1) | Germany | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4314880/germany-aim-120d-3-advanced-medium-range-air-to-air-missiles
2025-09-29 | 4230 | HIMARS (6) | GMLRS Pods (750, various variants); ATACMS (200) | Estonia | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of 18 of 29 HIMARS ordered; already received 11. | https://www.govinfo.gov/content/pkg/CREC-2025-09-29/pdf/CREC-2025-09-29.pdf
2025-09-30 | 705 | HIMARS (48) |  | Australia | Indo-Pacific | Yes (Primary) | Taiwan is waiting for delivery of 18 of 29 HIMARS ordered; already received 11. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4318640/australia-m142-high-mobility-artillery-rocket-systems
2025-09-30 | 30 | KGV-135A Commmunications Security Devices |  | Japan | Indo-Pacific | Yes (Potential) | This is a subcomponent of the AIM-120. Taiwan is waiting on delivery of AIM-120s from a couple of FMS cases. This subcomponent might be part of those sales but it is not clear. | https://www.govinfo.gov/content/pkg/CREC-2025-09-30/pdf/CREC-2025-09-30.pdf
2025-10-01 | 34 | AGM-65G2 Maverick Tactical Missiles (44) |  | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4320021/republic-of-korea-agm-65g2-maverick-tactical-missiles
2025-10-01 | 1750 | HIMARS (26) | GMLRS Pods (328, various variants); ATACMS Pods (64) | Canada | North America (NATO) | Yes (Primary) | Taiwan has received an initial batch of HIMARS launchers and ATACMS pods but is waiting on delivery of additional launchers and GMLRS pods. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4320012/canada-m142-high-mobility-artillery-rocket-systems
2025-10-02 | 85 | OT-228/U Common Infrared Countermeasures (10) |  | Netherlands | Europe (NATO) | Potential | Infrared countermeasure systems for CH-47 Chinook helicopters. Taiwan also operates this type of helicopter and some arms sales for maintenance support of aircraft might include these countermeasure systems. However, we don't know for sure. | https://www.govinfo.gov/content/pkg/CREC-2025-10-02/pdf/CREC-2025-10-02.pdf
2025-10-06 | 3131 | AIM-120D-3 AMRAAM (997) | AMRAAM D-3 Guidance Sections (119) | Belgium | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of several AIM-120 variants from a sale of F-16 munitions and NASAMS. | https://www.govinfo.gov/content/pkg/CREC-2025-10-06/pdf/CREC-2025-10-06.pdf
2025-10-06 | 135 | Follow On Technical Support for Offshore Patrol Vessels and Patrol Boats |  | Iraq | Middle East | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-10-06/pdf/CREC-2025-10-06.pdf
2025-10-31 | 353 | Ebbing Air National Guard Base Construction Services |  | Singapore | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4327329/singapore-ebbing-air-national-guard-base-construction-services
2025-11-06 | 100 | AIM-9X Block II Missiles (120) | Missile Containers; Training Aids; Active Optical Targeting Detectors; Spares; Support Equipment | Poland | Europe (NATO) | Potential | Taiwan is waiting on delivery of AIM-9X missiles, but a different variant than the one in this arms sale. There is likely some commonality/overlapping components but it is not a one to one overlap. | https://www.govinfo.gov/content/pkg/CREC-2025-11-06/pdf/CREC-2025-11-06.pdf
2025-11-07 | 230 | Sustainment of G-550 Aircraft Modified with AISREW Mission Systems |  | Australia | Indo-Pacific | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-11-07/pdf/CREC-2025-11-07.pdf
2025-11-12 | 318 | AIM-9X Block II Missiles (340) | AIM-9X Block II tactical guidance units (34) | Denmark | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of AIM-9X Block II missiles. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4329708/denmark-aim-9x-block-ii-tactical-missiles
2025-11-13 | 100 | Country Wide Repeater System |  | Iraq | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4330710/iraq-country-wide-repeater-system
2025-11-14 | 3500 | SM-6 Block 1 Missiles (173); SM-2 Block IIIC Missiles (577) | Mk-21 VLS canisters; Mk-13 VLS canisters; various support equipment | Germany | Europe (NATO) | No | Taiwan operates the SM-2 missile, but is not currently waiting on delivery from the United States. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4332014/germany-standard-missile-6-block-i-and-standard-missile-2-block-iiic
2025-11-18 | 105 | Patriot Air Defense System Sustainment | Upgrade from M901 to M903 launcher configuration | Ukraine | Europe (Non-NATO) | Yes (Potential) | Taiwan operates the Patriot system and the US has recently sold Patriot maintenance equipment and services to Taiwan. However, since our dataset does not track delivery of maintenance equipment or services we cannot say for sure if these are "backlogged." | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4334941/ukraine-patriot-air-defense-system-sustainment
2025-11-18 | 755 | Electromagnetic Aircraft Launch System (1) | Launcher Configurations (3) | France | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-11-18/pdf/CREC-2025-11-18.pdf
2025-11-19 | 46 | FGM-148 Javelin Missiles (100) | Javelin Lightweight Command Launch Units (25) | India | Indo-Pacific | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4337533/india-javelin-missile-system
2025-11-19 | 47 | M982A1 Excalibur (216) |  | India | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4337518/india-excalibur-projectiles
2025-11-19 | 82 | GBU-53 SDB-II (28) |  | Japan | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4337497/japan-munitions
2025-11-20 | 158 | AIM-120C-8 AMRAAM (55) | AIM-120C-8 Guidance Sections (2) | Singapore | Indo-Pacific | Yes (Primary) | Taiwan is waiting on delivery of AIM-120 missiles as part of a sale of F-16 munitions and NASAMS batteries. | https://www.govinfo.gov/content/pkg/CREC-2025-11-20/pdf/CREC-2025-11-20.pdf
2025-11-24 | 200 | Advanced Extremely High Frequency (AEHF) Navy Multiband Terminals (6) |  | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4341361/united-kingdom-navy-multiband-terminals
2025-12-01 | 500 | Blanket Order Training Support |  | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4345481/kingdom-of-saudi-arabia-blanket-order-training
2025-12-01 | 500 | Cooperative Logistics Supply Support Arrangement Program | Cooperative Logistics Supply Support Arrangement | Saudi Arabia | Middle East | Potential | This FMS case covers ongoing logistics support for several types of US-made helicopters. Taiwan also operates these helicopters and could be purchasing logistics support from the US, but it is impossible to say for certain. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4345453/kingdom-of-saudi-arabia-cooperative-logistics-supply-support-arrangement-progra
2025-12-01 | 445 | F-16 Sustainment |  | Bahrain | Middle East | Potential | Taiwan has recently received F-16 spare and repair parts in FMS cases notified to Congress. However, we do not track logistics in our backlog dataset and it's difficult to determine precise components. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4345416/bahrain-f-16-sustainment
2025-12-02 | 430 | Follow on Technical Support for Perry-Class Frigates |  | Bahrain | Middle East | Potential | Taiwan also operates former Perry-class frigates and has recent FMS cases for logistics support for naval vessels. | https://www.govinfo.gov/content/pkg/CREC-2025-12-02/pdf/CREC-2025-12-02.pdf
2025-12-02 | 200 | Extension of Previously Notified Technical Support for MQ-9A unmanned aircraft. |  | Spain | Europe (NATO) | No | Taiwan has MQ-9B aircraft in the backlog, but since these have not arrived yet there is no overlap for sustainment services yet. | https://www.govinfo.gov/content/pkg/CREC-2025-12-02/pdf/CREC-2025-12-02.pdf
2025-12-04 | 2680 | Air Strike Weapons (various types and quantities) |  | Canada | North America (NATO) | No | This FMS case includes multiple types of air-launched bomb weapons, including SDB-I and SDB-II. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4348692/canada-air-strike-weapons
2025-12-05 | 112 | GBU-39/B SDB-I bombs (624) |  | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4351321/republic-of-korea-gbu-39b-small-diameter-bombs-increment-i-sdb-i
2025-12-05 | 301 | JASSM-ER Missiles (100) | KGV-135A Encryption Devices; Spare and Repair Parts | Italy | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4351311/italy-joint-air-to-surface-standoff-missiles-with-extended-range
2025-12-05 | 730 | AIM-120C-8 AMRAAM (200) | AIM-120C-8 Guidance Sections (3) | Denmark | Europe (NATO) | Yes (Primary) | Taiwan is waiting for delivery of several AIM-120 variants from multiple FMS cases. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4351295/denmark-aim-120c-8-advanced-medium-range-air-to-air-missiles
2025-12-05 | 91 | M1085A2 and M1078A2 MTVs |  | Lebanon | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4350902/lebanon-m1085a2-and-m1078a2-medium-tactical-vehicles
2025-12-05 | 3000 | IBCS Equipment |  | Denmark | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-12-08/pdf/CREC-2025-12-08-bk2.pdf
2025-12-05 | 260 | Various Support Equipment and Services for F-35 Aircraft |  | South Korea | Indo-Pacific | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-12-08/pdf/CREC-2025-12-08-bk2.pdf
2025-12-05 | 686 | Link-16 Systems (92) | Various other support equipment for F-16s | Pakistan | Indo-Pacific | Yes (Primary) | This FMS case upgrades Pakistan's fleet of F-16s with new equipment for cryptography and communications. Taiwan is also waiting for delivery of Link 16 equipment. | https://www.govinfo.gov/content/pkg/CREC-2025-12-08/pdf/CREC-2025-12-08-bk2.pdf
2025-12-08 | 79 | AGM-114 Hellfire Missiles (240) | Engineering and support services; consumables; spare parts | Belgium | Europe (NATO) | No | Taiwan has the Hellfire in its inventory but is not currently waiting on delivery of them. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4354471/belgium-hellfire-missiles
2025-12-09 | 124 | GBU-53 SDB-II (288) |  | Belgium | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2025-12-09/pdf/CREC-2025-12-09.pdf
2025-12-16 | 35 | M1151A1 Humvee (90) |  | Lebanon | Middle East | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4361462/lebanon-m1151a1-high-mobility-multi-purpose-wheeled-vehicles
2025-12-16 | 100 | Aegis Class Destroyer Support |  | Japan | Indo-Pacific | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4361445/japan-aegis-class-destroyer-support
2025-12-18 | 990 | F-16D Block 70/72 Aircraft without engines (4) | Various Supporting equipment and munitions | Slovakia | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of the same configuration of F-16s and multiple supporting equipment mentioned in this FMS case. | https://www.govinfo.gov/content/pkg/CREC-2025-12-18/pdf/CREC-2025-12-18.pdf
2025-12-18 | 136 | Stinger Service Life Extension Program Components, Parts, and Services |  | NATO Support and Procurement Agency | Europe (NATO) | Potential | Taiwan operates Stinger missiles and has several recent FMS cases for support services that might include components for Stingers. However, we cannot tell for sure based on existing information. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4364192/nato-support-and-procurement-agency-stinger-service-life-extension-program-comp
2025-12-22 | 200 | F-404 Engine Fans (200) |  | Spain | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4366877/spain-f-404-engine-fans
2025-12-22 | 951 | AMRAAM-ER Missiles (236) | AIM-120C-8 Guidance Sections (5) | Denmark | Europe (NATO) | Yes (Primary) | Taiwan is waiting for delivery of several AIM-120 variants from multiple FMS cases. | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4366864/denmark-advanced-medium-range-air-to-air-missiles-extended-range
2025-12-29 | 200 | Blanket Order Training Support |  | Poland | Europe (NATO) | No |  | http://dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4368289/poland-blanket-order-training
2025-12-29 | 1800 | P-8A Aircraft (3) | Various major communication and other aicraft subsystems | Denmark | Europe (NATO) | No |  | https://www.dsca.mil/Press-Media/Major-Arms-Sales/Article-Display/Article/4368281/denmark-multi-mission-maritime-patrol-and-reconnaissance-aircraft-p-8a

## Global FMS Cases 2022
Date of Sale | Dollar Amount (Millions) | Primary Capability Sold | Secondary Capabilities Sold | Country | Region | Taiwan Backlog Overlap | Overlap Explanation | Source | Additional Sources
2022-02-03 | 23.7 | Multifunctional Information Distribution System-Low Volume Terminals (MIDS-LVT) (31) | MIDS-LVT Block 1 Upgrade (11); MIDS-LVT Block 2 Upgrade (31) | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/saudi-arabia-multifunctional-information-distribution-system-low
2022-02-03 | 4210 | F-16C/D Block 70 fighter aircraft (12 Cs, 4 Ds) | Engines (21); multiple avionics for the aircraft; multiple guided and unguided munitions, no missiles | Jordan | Middle East | Yes (Primary) | Taiwan purchased the same type of F-16s from the United States in 2019. | https://www.dsca.mil/press-media/major-arms-sales/jordan-f-16-cd-block-70-aircraft
2022-02-08 | 70 | Guided Multiple Launch Rocket System (GMLRS) Rockets (114) | Reduced Range Practice Rockets (114) | Jordan | Middle East | Yes (Primary) | Taiwan did purchase HIMARS which uses the GMLRS rocket. The original DSCA announcement only mentions ATACMS in the Taiwan sale, but other reporting indicates Taiwan modified the purchase to include GMLRS. | https://www.dsca.mil/press-media/major-arms-sales/jordan-guided-multiple-launch-rocket-systems-gmlrs-alternate-warhead
2022-02-10 | 13900 | F-15ID fighter aircraft (36) | Aircraft engines (72 installed, 15 spares); multiple avionics for the aircraft | Indonesia | Indo-Pacific | Yes (Secondary) | Some overlap in avionics, particularly the MS-110 reconnaissance pod. But overlap is relatively minor. | https://www.dsca.mil/press-media/major-arms-sales/indonesia-f-15id-aircraft
2022-02-17 | 6000 | M1A2 SEPv3 Abrams tanks (250) | Counter-IED systems (250); M88A2 Hercules Combat Recovery Vehicles (26); M1110 joint assault bridges (17); M2 .50 caliber machine guns (276); M240C 7.62mm machine guns (500); various 120mm tank ammunition rounds | Poland | Europe (NATO) | Yes (Primary) | Taiwan's Abrams tanks are built to a slightly different specification, but there is a great deal of overlap between them. | https://www.dsca.mil/press-media/major-arms-sales/poland-m1a2-sepv3-main-battle-tank
2022-02-22 | 122 | Large Aircraft Infrared Countermeasures (LAIRCM) for C-17, KC-30, and C-130 aircraft | LAIRCM System Processor Replacements (27); Guardian Laser Turret Assemblies (30); replacements and other sensors, unspecified quantity | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-laircm-line-replaceable-units-lrus
2022-03-15 | 950 | MH-60R Helicopters (8) | Helicopter engines (20); Hellfire missiles (32); various other munitions, avionics, and munition launch equipment | Spain | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/spain-mh-60r-multi-mission-helicopters-support
2022-03-17 | 700 | Ballistic Missile Defense Radar (BMDR) (1) and Command and Control Battle Management and Communications (C2BMC) nodes (2) | Combined radar-equipment shelter; encryption devices; secure communication equipment | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-ballistic-missile-defense-radar-bmdr-and-command-and
2022-03-24 | 176 | M270 Multiple Launch Rocket System (MLRS) Upgrades (9) | Various hardware related to the upgrade; 2 years of spare parts | Bahrain | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/bahrain-m270-multiple-launch-rocket-systems-mlrs-upgrade
2022-04-04 | 1673 | F-16C/D Block 70 fighter aircraft (4 Cs, 4 Ds) | Engines (11); multiple avionics for the aircraft; multiple munitions including AMRAAM, AIM-9X, and JDAM | Bulgaria | Europe (NATO) | Yes (Primary) | Taiwan purchased the same type of F-16s from the United States in 2019. Additionally, significant overlap between munitions for the Bulgarian F-16s and Taiwan's F-16s. | https://www.dsca.mil/press-media/major-arms-sales/bulgaria-f-16-cd-block-70-aircraft
2022-04-14 | 997 | AH-1Z Attack Helicopters (12) | Helicopter engines (28); weapon guidance systems; 20mm cannons | Nigeria | Africa | No |  | https://www.dsca.mil/press-media/major-arms-sales/nigeria-ah-1z-attack-helicopter-related-fms-acquisitions
2022-04-19 | 42 | Multifunctional Information Distribution System Joint Tactical Radio System (MIDS JTRS) (106) | MIDS JTRS terminals; LVT Cryptographic Modules; upgrade and retrofit kits for existing radio systems | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-defense-articles-related-multifunctional-information
2022-04-25 | 165 | Non-Standard Ammunition |  | Ukraine | Europe (Non-NATO) | No | Ammunition is for Soviet and Russian designed artillery and mortars in Ukraine's arsenal. No overlap with Taiwan ammunition. | https://www.dsca.mil/press-media/major-arms-sales/ukraine-non-standard-ammunition
2022-05-19 | 691 | TOW 2A Radio Frequency Missiles (5,000) | Missile support equipment; spare parts; training | Egypt | Middle East | Yes (Partial) | Taiwan has also purchased TOW missiles, with delivery expected in 2024. Taiwan purchased the B variant while Egypt purchased the A variant. | https://www.dsca.mil/press-media/major-arms-sales/egypt-tow-2a-radio-frequency-rf-missiles-and-support
2022-05-26 | 117 | AIM-9X missiles (72 Block II and 43 Block II+) |  | Netherlands | Europe (NATO) | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-aim-9x-block-ii-missiles
2022-05-26 | 385 | HIMARS (20) | Various types of missiles and rockets, including ATACMS (10), GMLRS (150 of various types); radio equipment; practice rockets | Australia | Indo-Pacific | Yes (Primary) | Overlap in both the HIMARS launchers and the ammunition. | https://www.dsca.mil/press-media/major-arms-sales/australia-himars-launchers
2022-05-26 | 2600 | CH-47F Chinook Helicopters (23) | Helicopter engines (56); various avionics; various communication systems | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-ch-47f-chinook-helicopters\
2022-06-21 | 94 | AGM-88E2 Missiles (15) | Various guidance systems, rocket motors, and warheads for the missiles. | Australia | Indo-Pacific | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/australia-agm-88e2-aargm-e2-missiles
2022-06-22 | 22.7 | Precision Guided Munitions (gravity bombs) | GBU-39/B Small Diameter Bombs (239); Mk-82 500 pound general purpose bombs (204); BLU-109 2,000 pound Hard Target Penetrator bombs (50) | Various | Europe (NATO) | No | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/nato-support-and-procurement-agency-nspa-precision-guided-munitions
2022-07-15 | 130 | Mk 54 Lightweight Torpedoes (31) | Recoverable Exercise Torpedo; spare parts; air launch accessories for rotary wing | South Korea | Indo-Pacific | No | Taiwan purchased torpedo conversion kits in 2017, but these kits would upgrade torpedoes already in Taiwan's arsenal. | https://www.dsca.mil/press-media/major-arms-sales/korea-mk-54-lightweight-torpedoes
2022-07-15 | 500 | HIMARS (6) | Various types of rocket ammunition for the HIMARS system, 36 each of GMLRS alternative warhead, unitary high explosive, and extended range variants; ATACMS (18) | Estonia | Europe (NATO) | Yes (Primary) | Overlap in both the HIMARS launchers and the ammunition. | https://www.dsca.mil/press-media/major-arms-sales/estonia-m142-high-mobility-artillery-rocket-system-himars
2022-07-15 | 950 | AIM-120 air to air missiles (205 D, 60 C-8 or D) | AIM-120 control sections, captive air training missiles, containers; integration support and test equipment | Norway | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/norway-aim-120-c-8-or-d-advanced-medium-range-air-air-missiles
2022-07-21 | 206 | Oceanographic Observation Equipment Systems |  | UAE | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-oceanographic-observation-equipment-system
2022-07-21 | 235 | AGM-158B (JASSM-ER) air-to-ground missiles (80) | Missile containers, support equipment, spare parts | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-joint-air-surface-standoff-missiles-extended-range-jassm-er
2022-07-21 | 397 | Weapons for Eurofighter Typhoon | AIM-120 C-7/8 AMRAAM (60); Mk-83 2,000 pound bombs (250); Mk-83 1,000 pound bombs (501); JDAM Tail Kits (350); other gravity bombs | Kuwait | Middle East | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/kuwait-advanced-weapons-support-eurofighter-typhoon-aircraft-program
2022-07-21 | 1219 | Patriot GEM-T Missiles (96) | Various support equipment and training equipment. | Netherlands | Europe (NATO) | Potential | Taiwan operates Patriot systems, and US sales of maintenance support mention the GEM missile variant, but it is unclear if Taiwan is waiting on delivery of additional interceptors. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-patriot-mim-104e-guidance-enhanced-missile-tactical-gem-t
2022-07-25 | 293 | AIM-120 air to air missiles (C-7/8 variants) (150) | AMRAAM Guidance Sections (3); missile containers and control sections; spare parts | Japan | Indo-Pacific | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-120c-78-advanced-medium-range-air-air-missiles-amraams
2022-07-25 | 630 | Munitions for F-15SG fighter aircraft | Gravity bombs of various size and guidance | Singapore | Indo-Pacific | Yes (Secondary) | Taiwan did purchase some JDAM guidance kits that overlap with the guidance kits in this sale in their 2019 purchase of F-16s. The overlap is relatively small. | https://www.dsca.mil/press-media/major-arms-sales/singapore-munitions-and-follow-training-and-sustainment-peace-carvin-v
2022-07-28 | 8400 | F-35 fighter aircraft (35) | Various munitions, including AIM-120 C-8 AMRAAM (105); AIM-9X (75 Block II+); JDAM guidance kits | Germany | Europe (NATO) | Yes (Secondary) | Overlap in AMRAAM, AIM-9X, and JDAM tail kits | https://www.dsca.mil/press-media/major-arms-sales/germany-f-35-aircraft-and-munitions
2022-08-01 | 300 | Javelin Lightweight Command Launch Units (513) | Javelin Outdoor Trainers; vehicle launcher electronics; technical assistance | United Kingdom | Europe (NATO) | No | While Taiwan operates Javelin systems, the Lightweight Command Launch Unit is a recent development that reached initial low-rate production in 2022. Taiwan has not purchased the lighweight variant yet. | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-javelin-lightweight-command-launch-units
2022-08-02 | 2245 | THAAD Interceptors (96) | Launch Control Stations (2); Tactical Operations Stations (2); spare parts; support and testing equipment | UAE | Middle East | No | Taiwan does not operate the THAAD system. | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-terminal-high-altitude-area-defense-thaad-system
2022-08-02 | 3050 | Patriot GEM-T Missiles (300) | Tools and test equipment; training equipment; spare parts | Saudi Arabia | Middle East | Potential | Taiwan operates Patriot systems, and US sales of maintenance support mention the GEM missile variant, but it is unclear if Taiwan is waiting on delivery of additional interceptors. | https://www.dsca.mil/press-media/major-arms-sales/saudi-arabia-patriot-mim-104e-guidance-enhanced-missile-tactical
2022-08-09 | 74 | Javelin Missiles (222) | Javelin Command Launch Units (33); missile simulation rounds; technical assistance | Brazil | Latin America | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/brazil-javelin-missiles
2022-08-25 | 141 | Ground Command and Control Equipment | MIDS-JTRS systems (6); KY-100 Narrowband Terminalsl KIV-78 and 77 Cryptographic Appliques | Morocco | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/morocco-ground-command-and-control
2022-08-25 | 1950 | UH-60M Blackhawk Helicopters (40) | Helicopter Engines; avionics; radio equipment | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-uh-60m-black-hawk-helicopters
2022-10-06 | 3000 | NASAMS Medium Range Air Defense System (7) | AIM-120 C-8 AMRAAM (63); AMRAAM-ER (63); AIM-9X (63); various communication and electronic systems | Kuwait | Middle East | Yes (Secondary) | Taiwan has not purchased the NASAM system yet, but it is expected to purchase in 2024 due to competing demands on production, including from Ukraine. Taiwan has purchased AIM-120 C-8 and AIM-9X missiles in its 2023 purchase of F-16 munitions | https://www.dsca.mil/press-media/major-arms-sales/kuwait-national-advanced-surface-air-missile-system-nasams-medium | https://gagadget.com/en/weapons/172996-taiwan-will-buy-nasams-air-defense-systems-to-defend-against-china/
2022-10-20 | 450 | SM-6 Block 1 Missiles (32) | Mk-21 VLS canisters; handling equipment; spare parts | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-standard-missile-6-block-i-sm-6-blk-i-missiles
2022-11-02 | 535 | GMLRS Rocket Pods, various quantities and types of warhead |  | Finland | Europe (NATO) | Yes (Primary) | Taiwan has purchased GMLRS rockets as part of the 2020 HIMARS sale. | https://www.dsca.mil/press-media/major-arms-sales/finland-guided-multiple-launch-rocket-systems-gmlrs
2022-11-02 | 6350 | C-130 J-30 Transport Aircraft (24) | Aircraft engines; spare parts; avionics and radio equipment | Australia | Indo-Pacific | No | Taiwan operates C-130 aircraft but it does not have any in the backlog. | https://www.dsca.mil/press-media/major-arms-sales/australia-c-130j-30-aircraft
2022-11-08 | 380 | AMRAAMs for F-16 and F-35 aircraft (120 C-8 variant) | Spare control sections and containers, AMRAAM C-8 Guidance Sections (10) | Belgium | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/belgium-advanced-medium-range-air-air-missiles-f-16-and-f-35-programs
2022-11-09 | 385 | AGM-154C Joint Stand Off Weapons (48) | Various test items, spares, and repair equipment. | Oman | Middle East | Yes (Primary) | Taiwan purchased AGM-154Cs in 2017. Delivery was expected in 2023, but no confirmation that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/oman-joint-stand-weapons-jsow
2022-11-09 | 495 | HIMARS (8) | GMLRS Missile Pods of various warhead types (36 apiece, 4 types); ATACMS missile pods (18) | Lithuania | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/lithuania-m142-high-mobility-artillery-rocket-system-himars
2022-11-15 | 700 | PAC-3 MSE missiles (72) | Telemetry kits; PAC-3 MSE trainers; launch stations items | Switzerland | Europe (Non-NATO) | Yes (Primary) | According to US reporting, the US modified a 2010 sale of Patriot systems to Taiwan in 2022 to include 100 MSE missiles for $882 million. | https://www.dsca.mil/press-media/major-arms-sales/switzerland-patriot-advanced-capability-pac-3-missile-segment-enhanced | https://www.bloomberg.com/news/articles/2022-12-05/us-upgrades-taiwan-weapons-package-with-newer-patriot-missiles?srnd=asia-politics&leadSource=uverify%20wall#xj4y7vzkg
2022-11-28 | 323 | AIM-9X missiles (40 Block II) and AGM-154 Joint Stand Off Weapons (48) |  | Finland | Europe (NATO) | Yes (Primary) | Taiwan purchsed AGM-154Cs in 2017 and AIM-9Xs in 2022 | https://www.dsca.mil/press-media/major-arms-sales/finland-aim-9x-block-ii-tactical-missiles-and-agm-154-joint-standoff
2022-11-29 | 1000 | Fixed Site-Low, Slow, Small Unmanned Aircraft System Integrated Defeat System (FS-LIDS) (10) | Coyote Block 2 interceptors (200); Counter Unmanned Electronic Warfare Systems; radio systems | Qatar | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/qatar-fixed-site-low-slow-small-unmanned-aircraft-system-integrated
2022-12-01 | 380 | FIM-92K Stinger MANPADS (350) | Production Verification Flight Test (PVFT) missiles (5) | Finland | Europe (NATO) | No | Taiwan purchased 250 FIM-92F Stingers in 2019. Press reports from 2023 indicated that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/finland-stinger-man-portable-ground-air-missiles | https://www.thedefensepost.com/2023/05/30/taiwan-stinger-missiles-us/
2022-12-06 | 1500 | CH-47F Chinook Helicopters (18) | Helicopter engines, avionics, and communication systems | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/korea-ch-47f-chinook-helicopters\
2022-12-06 | 3750 | M1A1 Abrams Tanks (116) | Hercules Combat Recovery Vehicles (12); Joint Assault Bridges (8); M577A3 Command Vehicles (6); Humvees (26); tank ammunition | Poland | Europe (NATO) | Yes (Primary) | The Abrams variant is unspecified but there is otherwise considerable overlap between the Poland sale and Taiwan's 2019 Abrams purchase. | https://www.dsca.mil/press-media/major-arms-sales/poland-m1a1-abrams-main-battle-tanks

## Global FMS Cases 2023
Date of Sale | Dollar Amount (Millions) | Primary Capability Sold | Secondary Capabilities Sold | Country | Region | Taiwan Backlog Overlap | Overlap Explanation | Source | Additional Sources
2023-02-07 | 10000 | HIMARS (18) | HIMARS Launcher Loader Module kits (468); ATACMS (45); various GMLRS warhead configuration rockets all in the 400s or 500s quantity | Poland | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/poland-high-mobility-artillery-rocket-system-himars-0
2023-02-09 | 55 | Air to Ground Munitions Kits and Equipment |  | Singapore | Indo-Pacific | Yes (Secondary) | Minor overlap in munitions mentioned in 2019 F-16 sale to Taiwan. | https://www.dsca.mil/press-media/major-arms-sales/singapore-air-ground-munitions-kits-and-services
2023-02-14 | 250 | Medical Information System |  | Kuwait | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kuwait-medical-information-system-kuwait-military-medical-command-kmmc
2023-02-16 | 670 | HIMARS (20) | ATACMS (80); various GMLRS warhead configuration rockets 30s quantity; unspecified number of support vehicles | Netherlands | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-m142-high-mobility-artillery-rocket-system-himars
2023-02-27 | 506 | Advanced Anti-Radiation Guided Missiles-Extended Range (63, AGM-88G variant) | Captive Air Training Missiles (20); AGM-88G Dummy Air Training Missiles | Australia | Indo-Pacific | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/australia-advanced-anti-radiation-guided-missiles-extended-range-aargm
2023-02-28 | 125 | Javelin Missiles (600, FGM-148F variant) |  | United Kingdom | Europe (NATO) | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-javelin-missiles
2023-03-07 | 60 | Javelin Missiles (255, FGM-148F variant) |  | Australia | Indo-Pacific | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/australia-javelin-fgm-148f-missiles
2023-03-07 | 1381 | E-2D Advanced Hawkeye Airborne Early Warning aircraft (5) | Aircraft engines (12); APY-9 Radars (5); avionics, radio, and electronic systems | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-e-2d-advanced-hawkeye-ahe-airborne-early-warning-and-control
2023-03-14 | 104 | Heavy Gun Carriers Joint Light Tactical Vehicles (95) |  | Romania | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/romania-m1278a1-heavy-gun-carriers-joint-light-tactical-vehicles-jltvs
2023-03-16 | 150 | Hellfire Missiles (800 AGM-114R2 variant) | Hellfire Captive Air Training Missiles (4); support and technical assistance | Poland | Europe (NATO) | No | Taiwan possesses Hellfire missiles, but does not currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/poland-hellfire-missiles
2023-03-16 | 895 | Tomahawk All Up Rounds (200 Block V, 20 Block IV) | Tactical Tomahawk Weapon Control System; Theater Mission Planning Center; various support equipment of unspecified quantity | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-tomahawk-weapon-system
2023-03-17 | 268 | Assault Amphibious Vehicles (63) | AAV command variant (9); AAV recovery variant (4); grenade launchers, thermal sight systems | Greece | Europe (NATO) | No | Taiwan possesses AAVs but it does not have currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/greece-assault-amphibious-vehicles-aavs
2023-03-29 | 350 | AH-1W Multi-Role Helicopter refurbishment (24) |  | Bahrain | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/bahrain-ah-1w-helicopter-refurbishment
2023-04-11 | 250 | AGM-154C Joint Stand Off Weapons (40) | Training missiles, containers, mission planning, integration support | Morocco | Middle East | Yes (Primary) | Taiwan purchased AGM-154Cs in 2017. Delivery was expected in 2023, but no confirmation that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/morocco-joint-stand-weapons-jsow
2023-04-11 | 524 | HIMARS (18) | ATACMs (40); GMLRS rockets with various ammunition (36 each of 2 variants); Humvees (9); practice rocket pods (40); various radio and vehicle equipment | Morocco | Middle East | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/morocco-high-mobility-artillery-rocket-systems-himars
2023-04-17 | 259 | F-16 Avionics Upgrade |  | Turkey | Europe (NATO) | No | Taiwan operates F-16 aircraft and purchased 66 C/D Block 70 in 2019 that have not been delivered. However, that sale does not indicate an overlap in avionics sold to Turkey. | https://www.dsca.mil/press-media/major-arms-sales/turkiye-f-16-avionics-upgrade
2023-04-28 | 31 | Advanced Precision Kill Weapon System-II (768) | Unspecified quantity of spares, support equipment, etc. | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-advanced-precision-kill-weapon-system-ii
2023-05-02 | 110 | Naval Strike Missile Coastal Defense System (1) | Unspecified quantity of training missiles, containers, mobile operational platforms | Latvia | Europe (NATO) | No | Taiwan does not operate the Naval Strike Missile system. But it would be a welcome asymmetric capability. | https://www.dsca.mil/press-media/major-arms-sales/latvia-naval-strike-missile-coastal-defense-system
2023-05-03 | 650 | Refurbishment and Modernization of AH-1Z (6) and UH-1Y (2) helicopters | Helicopter Engines (22); GPS navigation systems (14); radios (24) | Czech Republic | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/czech-republic-ah-1z-and-uh-1y-refurbishmentmodernization
2023-05-04 | 207 | Surveillance Towed Array Sensor System Expeditionary (SURTASS-E) (unspecified quantity) |  | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-surveillance-towed-array-sensor-system-expeditionary-surtass
2023-05-09 | 124 | AN/AAQ-33 Sniper Targeting Pods (34) |  | Poland | Europe (NATO) | Yes (Primary) | Taiwan has purchased Sniper targeting pods for F-16 aircraft, and in 2023 purchased an unspecified infrared track and targeting system that might be a Sniper though is unspecified | https://www.dsca.mil/press-media/major-arms-sales/poland-sniper-advanced-targeting-pods
2023-05-09 | 250 | Heavy Gun Carriers Joint Light Tactical Vehicles (192) | Unspecified quantites of various small arms, spare parts, other equipment | Slovakia | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/slovakia-m1278a1a2-heavy-gun-carriers-joint-light-tactical-vehicles
2023-05-11 | 8500 | CH-47F Helicopters (60) | Helicopter Engines (140); various helicopter avionics and communication equipment | Germany | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/germany-ch-47f-chinook-helicopters
2023-05-24 | 285 | NASAMS Medium Range Air Defense System (1) | Fire Distribution Center; canister launchers; other equipment | Ukraine | Europe (Non-NATO) | No | Taiwan has not purchased the NASAM system yet, but it is expected to purchase in 2024 due to competing demands on production, including from Ukraine. | https://www.dsca.mil/press-media/major-arms-sales/ukraine-national-advanced-surface-air-missile-system-nasams
2023-06-02 | 110 | Mk 41 VLS Launchers (8) |  | Netherlands | Europe (NATO) | No | Taiwan has purchased Mk 41 VLS systems from the US in the past but does not have any on order currently. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-mk-41-vertical-launching-system-vls
2023-06-14 | 48 | Excalibur Guided 155mm Artillery Shells (271) |  | Spain | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/spain-excalibur-projectiles
2023-06-16 | 611 | MQ-9A Block 5 Unmanned Aircraft (4) | Mobile Ground Control Systems (3); Embedded GPS Systems (30); AN/APY-8 Synthetic Aperture Radars (20) | Netherlands | Europe (NATO) | Yes (Partial) | Taiwan is waiting on delivery of 4 MQ-9B drones and associated support equipment. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-mq-9a-block-5-aircraft
2023-06-27 | 5900 | P-8A Maritime Patrol Aircraft (16) | MIDS JTRS (26); GPS systems (38); LAIRCM system (25) various avionics and sensors | Canada | North America (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/canada-p-8a-aircraft
2023-06-28 | 293 | GBU-53/B Small Diameter Bomb Increment II (580) |  | Norway | Europe (NATO) | Yes (Partial) | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/norway-small-diameter-bomb-ii
2023-06-28 | 4000 | Integrated Air and Missile Defense (IAMD) Battle Command System (IBCS) | Patriot M903 Launch Stations (48); PAC-3 MSE interceptors (644); Lower Tier Air and Missile Defense Sensors (LTAMDS) (12) | Poland | Europe (NATO) | Yes (Secondary) | According to US reporting, the US modified a 2010 sale of Patriot systems to Taiwan in 2022 to include 100 MSE missiles for $882 million. | https://www.dsca.mil/press-media/major-arms-sales/poland-integrated-air-and-missile-defense-iamd-battle-command-system-0
2023-06-29 | 5620 | F-35 Fighter Aircraft and Munitions (24) | Munitions include AIM-120 C-8 (70); Small Diameter Bombs Increment II (86); AIM-9X (50) | Czech Republic | Europe (NATO) | Yes (Secondary) | Overlap in AIM-120 C-8 missiles, Small Diameter Bombs, and AIM-9X | https://www.dsca.mil/press-media/major-arms-sales/czech-republic-f-35-aircraft-and-munitions
2023-06-30 | 105 | F-16 Modernization (32) |  | Romania | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/romania-modernization-tpt-f-16s
2023-07-07 | 203 | Hellfre Missiles (1,515) |  | France | Europe (NATO) | No | Taiwan possesses Hellfire missiles, but does not currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/france-hellfire-missiles
2023-07-07 | 605 | AIM-120 C-8 AMRAAM Missiles (250) | AMRAAM Guidance Sections (6); containers; test sets and telemetry kits | Sweden | Europe (Non-NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/sweden-aim-120c-8-advanced-medium-range-air-air-missile-amraam
2023-07-19 | 2900 | AIM-120 C-8 AMRAAM Missiles (969) | AMRAAM Guidance Sections (12); Captive Air Training Missiles; KGV-135A Communications Security devices | Germany | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://dsca.mil/press-media/major-arms-sales/germany-aim-120c-8-advanced-medium-range-air-air-missiles-amraam
2023-07-31 | 120 | Assault Amphibious Vehicles (16) | AAV command variant (3); AAV recovery variant (2); various machine guns | Romania | Europe (NATO) | No | Taiwan possesses AAVs but it does not have currently have any on order. | https://www.dsca.mil/press-media/major-arms-sales/romania-assault-amphibious-vehicles
2023-08-01 | 395 | M270 Multiple Launch Rocket System (MLRS) Upgrades (unspecified amount) |  | Finland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/finland-m270a2-multiple-launch-rocket-system-mlrs-upgrade
2023-08-18 | 975 | HIMARS (22) | GMLRS Missile Pods of various warhead types (190 total); support vehicles | Australia | Indo-Pacific | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/australia-m142-high-mobility-artillery-rocket-systems-himars
2023-08-21 | 12000 | AH-64E Apache Helicopters (96) | Helicopter Engines (210); various avionics and radar; munitions including Hellfire, JAGM, Stinger | Poland | Europe (NATO) | No | Taiwan operates the AH-64E, but it does not have any on order. | https://www.dsca.mil/press-media/major-arms-sales/poland-ah-64e-apache-helicopters
2023-08-28 | 104 | JASSM-ER Missiles (50) | JASSM Anti-jam GPS; training missiles; spare parts | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-joint-air-surface-standoff-missiles-extended-range-jassm-er
2023-09-01 | 1500 | Stryker Vehicles (183) | Modular Catastrophic Recovery Systems (5); M984A4 Wrecker HEMTT (5) various electronic and sensor components | Bulgaria | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/bulgaria-stryker-vehicles
2023-09-13 | 5060 | F-35 fighter aircraft (25) | Various avionics and support equipment | South Korea | Indo-Pacific | No | This package does not include munitions for the F-35s, which is the common area of overlap with Taiwan's backlog | https://www.dsca.mil/press-media/major-arms-sales/korea-f-35-aircraft
2023-09-15 | 313 | Munitions and Sensors for MQ-9B |  | Canada | North America (NATO) | Yes (Secondary) | Taiwan purchased 4 MQ-9B aircraft in November 2020. Munitions were not included in that sale, but there is overlap in some of the sensor and communication equipment | https://www.dsca.mil/press-media/major-arms-sales/taipei-economic-and-cultural-representative-office-united-states-18
2023-10-03 | 70 | TOW 2B Radio Frequency Missiles (301) |  | Oman | Middle East | Yes (Primary) | Taiwan has purchased 460 TOW 2B missiles with delivery expected in 2024 | https://www.dsca.mil/press-media/major-arms-sales/oman-tow-2b-radio-frequency-missiles-bgm-71f-7-rf-and-support
2023-10-04 | 2800 | Patriot Configuration 3+ Modernized Fire Units (4) | PAC-3 MSE missiles (51); Patriot M903 launch stations (24); AN/MPQ-65 radar sets (4) | Spain | Europe (NATO) | Yes (Secondary) | According to US reporting, the US modified a 2010 sale of Patriot systems to Taiwan in 2022 to include 100 MSE missiles for $882 million. | https://dsca.mil/press-media/major-arms-sales/spain-patriot-configuration-3-modernized-fire-units
2023-10-23 | 100 | AIM-120 C-8 AMRAAM Missiles (36) | Various support equipment and training equipment. | Lithuania | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/lithuania-aim-120c-8-advanced-medium-range-air-air-missiles-amraam
2023-10-23 | 500 | Anti-Radiation Guided Missiles-Extended Range AGM-88G (150) |  | Finland | Europe (NATO) | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/finland-advanced-anti-radiation-guided-missiles-extended-range-aargm
2023-10-23 | 957 | Joint Air-to-Ground Missiles (JAGM) (3,000) | Dummy missiles; technical assistance; training support | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-joint-air-ground-missiles-jagm
2023-10-24 | 74 | Rolling Airframe Missile Block 2B (63) |  | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-rolling-airframe-missiles-ram-block-2b-tactical-missiles
2023-10-24 | 220 | HIMARS (6) | GMLRS rocket pods of various warhead types (24, 2 variants); ATACMS (10) | Latvia | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. Also an overlap in HIMARS munitions. | https://www.dsca.mil/press-media/major-arms-sales/latvia-m142-high-mobility-artillery-rocket-systems
2023-11-09 | 2530 | M1A2 SEPv3 Abrams tanks (54) | M88A2 Hercules Combat Recovery Vehicles (4); Joint Assault Bridges (4); Heavy Assault Scissor Bridges (4); lots of tank ammunition | Romania | Europe (NATO) | Yes (Primary) | Taiwan's Abrams tanks are built to a slightly different specification, but there is a great deal of overlap between them. | https://www.dsca.mil/press-media/major-arms-sales/romania-m1a2-abrams-main-battle-tanks
2023-11-14 | 650 | SM-6 Block 1 Missiles (38) | Mk-21 VLS canisters; handling equipment; spare parts | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/korea-standard-missile-6-block-i-sm-6-blk-i
2023-11-15 | 52 | AIM-9X Missiles (42) | Captive Air Training Missiles (5); AIM-9X Guidance Units (5) | South Korea | Indo-Pacific | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/korea-aim-9x-block-ii-and-block-ii-plus-sidewinder-missiles
2023-11-17 | 2350 | Tomahawk All Up Rounds (200 Block IV; 200 Block V) | Tactical Tomahawk Weapon Control System (14) and other components | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-tomahawk-weapon-system
2023-12-01 | 271 | F-35 Munitions (various quantities) | AIM-120C-8 (39); JDAM Guidance Kits; gravity bombs (various); GBU-53 SDB-I (118) | South Korea | Indo-Pacific | Yes (Primary) | AIM-120C-8 overlap, some JDAM tail kit overlap | https://www.dsca.mil/press-media/major-arms-sales/korea-f-35-munitions
2023-12-04 | 85 | AN/TPQ-50 Radar (18, man portable versions) | Various support equipment and training equipment. | UAE | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-antpq-50-radar
2023-12-04 | 582 | RE-3A Tactical Airborne Surveillance System Modernization | Various electronic communication and guidance systems. | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/saudi-arabia-re-3a-tactical-airborne-surveillance-system-aircraft
2023-12-07 | 300 | MK 54 Lightweight Torpedoes (80) | Various spare parts and support equipment | Germany | Europe (NATO) | No | Taiwan purchased lightweight torpedo conversion kits, not all up rounds. | https://www.dsca.mil/press-media/major-arms-sales/germany-mk-54-lightweight-torpedoes
2023-12-09 | 106 | M830A1 120mm Tank Cartridges (13,981) |  | Israel | Middle East | Yes (Potential) | Taiwan purcahsed 120mm tank rounds as part of the big Abrams sale. | https://www.dsca.mil/press-media/major-arms-sales/israel-m830a1-120mm-tank-cartridges
2023-12-12 | 80 | Javelin Missiles (263) |  | Romania | Europe (NATO) | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/romania-javelin-missiles
2023-12-13 | 255 | Communications Equipment | Various quantities and types of radios and other electronic equipment | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-communications-equipment
2023-12-15 | 59 | AIM-9X Block II Missiles (44) |  | Japan | Indo-Pacific | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-9x-block-ii-sidewinder-missiles
2023-12-15 | 224 | AIM-120C-8 AMRAAM Missiles (120) |  | Japan | Indo-Pacific | Yes (Primary) | Taiwan has also purchased AIM-120C-8 missiles for its F-16 fleet. | https://www.dsca.mil/press-media/major-arms-sales/japan-aim-120c-8-advanced-medium-range-air-air-missiles-amraam
2023-12-15 | 400 | HIMARS (21) | Communication and support equipment, but no mention of HIMARS ammunition quantities in the sale. | Italy | Europe (NATO) | Yes (Primary) | Taiwan purchased HIMARS in 2020 that have not started delivery yet. | https://www.dsca.mil/press-media/major-arms-sales/italy-m142-high-mobility-artillery-rocket-systems-himars
2023-12-15 | 1950 | UH-60M Blackhawk Helicopters (35) | Various spare parts and support equipment | Greece | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/greece-uh-60m-black-hawk-helicopters
2023-12-22 | 780 | FIM-92K Stinger MANPADS (940) |  | Various | Europe (NATO) | No | Taiwan purchased 250 FIM-92F Stingers in 2019. Press reports from 2023 indicated that delivery was completed. | https://www.dsca.mil/press-media/major-arms-sales/nato-support-and-procurement-agency-nspa-stinger-missiles
2023-12-29 | 147 | 155mm Artillery Shells |  | Israel | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/israel-155mm-artillery-ammunition

## Global FMS Cases 2024
Date of Sale | Dollar Amount (Millions) | Primary Capability Sold | Secondary Capabilities Sold | Country | Region | Taiwan Backlog Overlap | Overlap Explanation | Source | Additional Sources
2024-01-10 | 129 | 28-Meter Patrol Craft Kits |  | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-28-meter-patrol-craft-kits
2024-01-10 | 200 | Light Tactical Vehicle Chassis and Fleet Build |  | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-light-tactical-vehicle-chassis-and-fleet-build
2024-01-10 | 250 | Tomahawk Weapons System Support Services |  | Australia | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/australia-general-tomahawk-weapons-system-support-services-uplift
2024-01-11 | 75 | Javelin Missiles (246) | Lightweight Javelin Command Launch Units (6) | Kosovo | Europe (Non-NATO) | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/kosovo-javelin-missiles
2024-01-26 | 500 | Black Hawk Helicopters (8) | Helicopter engines, avionics, and communication systems | Croatia | Europe (NATO) | No | Taiwan operates the same variant of Black Hawk helicopters, but it is not waiting on any orders. | https://www.dsca.mil/press-media/major-arms-sales/croatia-uh-60m-black-hawk-helicopters-0
2024-01-26 | 8600 | F-35 Aircraft (40) | Aircraft engines, avionics, radar, no ammunition | Greece | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/greece-f-35-joint-strike-fighter-conventional-take-and-landing-ctol
2024-01-26 | 23000 | F-16 aircraft (40 new build, 79 modifications to existing airframes) | Aircraft engines, avionics, radar, lots of munitions | Turkey | Europe (NATO) | Yes (Primary) | Taiwan waiting on delivery of the same F-16 model (C/D Block 70), which is scheduled to complete in 2026. | https://www.dsca.mil/press-media/major-arms-sales/turkiye-f-16-aircraft-acquisition-and-modernization
2024-02-01 | 3990 | MQ-9B Sky Guardian UAVs (31) | Sensors, guidance and navigation systems, Hellfire missiles (170) | India | Indo-Pacific | Yes (Partial) | Taiwan has 4 MQ-9Bs in the backlog. However, Taiwan has ordered the maritime surveillance variant while India has ordered the air surveillance variant | https://www.dsca.mil/press-media/major-arms-sales/india-mq-9b-remotely-piloted-aircraft
2024-02-02 | 150 | AGM-114R2 Hellfire Missiles (386) | Various technical documents and support equipment | Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/netherlands-hellfire-missiles
2024-02-05 | 908 | JASSM-ER Missiles (120) | Separation test vehicles (2), instrument test vehicle (1), encryption devices | Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/netherlands-joint-air-surface-standoff-missiles-extended-range
2024-02-07 | 1200 | Airspace and Surface Radar Aerostat Systems | Airborne Early Warning radars with IFF capability; mooring systems; fiber optics | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-aerostat-systems
2024-02-15 | 69 | AIM-120C-8 AMRAAM Missiles (12) |  | Italy | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/italy-aim-120c-8-advanced-medium-range-air-air-missiles | This sale announcement amends/updates an earlier sale of AIM-120s to Italy that fell beneath the reporting requirement thresholds.The new sale value is above the thresholds
2024-02-15 | 150 | Small Diameter Bomb II (125) |  | Italy | Europe (NATO) | Yes (Partial) | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/italy-small-diameter-bomb-ii
2024-02-27 | 281 | HF, VHF, and UHF Radios |  | Germany | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/germany-high-frequency-very-high-frequency-and-ultra-high-frequency
2024-03-07 | 170 | BQM-177A Subsonic Sea-Skimming Aerial Targets (5) | GQM-163 target drones, classified technical publications, personnel training | South Korea | Ino | No | For the ROKN's KDX-III Batch II Aegis destroyers | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-subsonic-sea-skimming-aerial-targets-kdx-iii-batch-ii
2024-03-07 | 138 | Telecommunications services for SATCOM access to Canadian armed forces |  | Canada | North America (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/canada-mobile-user-objective-system-access
2024-03-08 | 350 | T-700 GE 401C or 401D Engines for MH-60R Helicopters (6) | Spare engine containers, repair parts, ferry support, publications | South Korea | Indo-Pacific | No | Taiwan operates Blackhawk Helicopters of a different variant. No engines currently for these helicopters in the backlog as of March 2024 | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-engines-and-sustainment-mh-60r-multi-mission
2024-03-08 | 111 | Joint Light Tactical Vehicle Heavy Gun Carriers (18) and General Purpose (7) |  | North Macedonia | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/north-macedonia-joint-light-tactical-vehicles
2024-03-12 | 219 | AIM-9X Block II Missiles (232) | AIM-9X Missile Guidance Units (16), containers, spare parts, active optical detectors | Poland | Europe (NATO) | Yes (Primary) | Taiwan purchased AIM-9X missiles in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/poland-aim-9x-block-ii-sidewinder-missiles
2024-03-12 | 1690 | AIM-120C-8 AMRAAM (745) | AMRAAM Guidance Sections (16), LAU-129 Guided Missile Launchers (50), other spares | Poland | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/poland-aim-120c-8-advanced-medium-range-air-air-missiles
2024-03-12 | 1770 | AGM-158B-2 JASSM-ER Missiles (821) | Test equipment, weapon support and integration. | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-agm-158b-2-joint-air-surface-standoff-missile-extended-range
2024-03-15 | 91 | AIM-9X Block II+ Missiles (28) | Tactical Guidance Units (4), Captive Training Missiles (8), etc. | Italy | Europe (NATO) | Yes (Partial) | Taiwan purchased AIM-9X missiles in September 2022. These missiles were just Block II and not II+. Unclear what the difference is. | https://www.dsca.mil/press-media/major-arms-sales/italy-aim-9x-sidewinder-missiles
2024-03-19 | 2200 | M1A2 SEPv3 Abrams Tanks (50) | Hercules Combat Recovery Vehicles (4); Joint Assault Bridgets (8); Assault Breacher Vehicles (8); Ammunition | Bahrain | Middle East | Yes (Primary) | Taiwan purchased Abrams tanks in 2019 that are scheduled for delivery from 2024-2026. Taiwan has a slightly different Abrams variant, but it is mostly the same. | https://www.dsca.mil/press-media/major-arms-sales/bahrain-m1a2-abrams-main-battle-tanks
2024-03-19 | 260 | Javelin FGM-148F Missiles (612) | Javelin Lightweight Command Launch Units (200) | Morocco | Middle East | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/morocco-javelin-missiles
2024-04-09 | 138 | HAWK Phase III Missile System Sustainment |  | Ukraine | Europe (Non-NATO) | No | Tiawan retired its HAWK air defense systems in 2023 | https://www.dsca.mil/press-media/major-arms-sales/ukraine-hawk-phase-iii-missile-system-sustainment
2024-04-10 | 101 | Multifunctional Information Distribution Systems (50) | MIDS-LVT Block Upgrade 2 Retrofit Kits (100) | Saudi Arabia | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-multifunctional-information-distribution-systems
2024-04-15 | 140 | C-172 and AC/RC-208 Aircraft Logistics Support |  | Iraq | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/iraq-c-172-and-acrc-208-aircraft-contractor-logistics-support
2024-04-18 | 143 | BT-67 Aircraft (unknown quantity) |  | Argentina | Latin America | No |  | https://www.dsca.mil/press-media/major-arms-sales/argentina-basler-bt-67-aircraft
2024-04-24 | 1275 | AARGM-ER Missiles (360) | AGM-88GAARGM-ER Guidance Sections (8 spares); AGM-88G AARGM-ER Control Sections (8 spares); various spare and repair parts | Poland | Europe (NATO) | No | Taiwan has AGM-88s in the backlog, but not the AARGM-ER model. | https://www.dsca.mil/press-media/major-arms-sales/poland-advanced-anti-radiation-guided-missiles-extended-range
2024-04-24 | 700 | AARGM-ER Missiles (265) | AGM-88GAARGM-ER Guidance Sections (8 spares); AGM-88G AARGM-ER Control Sections (8 spares); various spare and repair parts | Netherlands | Europe (NATO) | No | Taiwan has AGM-88s in the backlog, but not the AARGM-ER model. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-advanced-anti-radiation-guided-missiles-extended-range
2024-05-06 | 80 | AN/AAQ-33 Sniper Targeting Pods (10) |  | Malaysia | Indo-Pacific | Yes (Primary) | Taiwan has purchased Sniper targeting pods for F-16 aircraft, and in 2023 purchased an unspecified infrared track and targeting system that might be a Sniper though is unspecified | https://www.dsca.mil/press-media/major-arms-sales/malaysia-sniper-advanced-targeting-pods
2024-05-07 | 144 | HARM Control Section Modification (HCSM) Upgrade Kits (149) |  | UAE | Middle East | No | Taiwan is waiting on delivery of HARM missiles, but they have not purchased the HCSM | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-high-speed-anti-radiation-missile-harm-control
2024-05-10 | 30 | HIMARS (3) |  | Ukraine | Europe (Non-NATO) | Yes (Primary) | Emergency FMS case that involves immediate sale of launchers financed by Germany. | https://www.dsca.mil/press-media/major-arms-sales/ukraine-high-mobility-artillery-rocket-systems
2024-05-14 | 300 | AIM-9X Block II (300) | AIM-9X Missile Guidance Units (40); Captive Air Training Missiles (40); Guidance Units for training missiles (20) | Romania | Europe (NATO) | Yes (Primary) | Taiwan purchased AIM-9X missiles in 2022 that it has not received yet. | https://www.dsca.mil/press-media/major-arms-sales/romania-aim-9x-sidewinder-block-ii-missiles
2024-05-21 | 96 | JDAM Tail Kits (790 various models) |  | Canada | North America (NATO) | No | Taiwan is not waiting on delivery of JDAM kits. | https://www.dsca.mil/press-media/major-arms-sales/canada-joint-direct-attack-munition-tail-kits
2024-05-24 | 950 | UH-60M Black Hawk Helicopters (12) | Various spare parts and support equipment, including engines (34), GPS systems (28), radio systems (24), etc. | Brazil | Latin America | No | Taiwan operates the UH-60M helicopter, but there are currently none in the arms sale backlog. | https://www.dsca.mil/press-media/major-arms-sales/brazil-uh-60m-black-hawk-helicopters-0
2024-05-29 | 1050 | UH-60M Black Hawk Helicopters (12) | Various spare parts and support equipment. | Austria | Europe (NATO) | No | Taiwan operates the UH-60M helicopter, but there are currently none in the arms sale backlog. | https://www.dsca.mil/press-media/major-arms-sales/austria-uh-60m-blackhawk-helicopters
2024-05-29 | 900 | UH-60M Black Hawk Helicopters (12) | Various spare parts and support equipment | Sweden | Europe (NATO) | No | Taiwan operates the UH-60M helicopter, but there are currently none in the arms sale backlog. | https://www.dsca.mil/press-media/major-arms-sales/sweden-uh-60m-black-hawk-helicopters
2024-06-07 | 215 | AIM-120C-8 Missiles (84) | AIM-120C-8 guidance sections (3); various spare and support equipment | Denmark | Europe (NATO) | Yes (Primary) | AIM-120C-8 is in the backlog. | https://www.dsca.mil/press-media/major-arms-sales/denmark-aim-120c-8-advanced-medium-range-air-air-missiles
2024-06-11 | 1940 | AIM-120C-8 Missiles (300) | AIM-120C-8 guidance sections (20); various spare and support equipment | Norway | Europe (NATO) | Yes (Primary) | AIM-120C-8 is in the backlog. | https://www.dsca.mil/press-media/major-arms-sales/norway-aim-120c-8-advanced-medium-range-air-air-missiles
2024-06-13 | 678 | AMRAAM-ER Missiles (174) | KGV-135A cryptographic devices; ADU-891 Adaptor Group Test Sets | Netherlands | Europe (NATO) | Potential | Taiwan is waiting on delivery of AIM-120C-8s which are similar to but not exactly the same as the AMRAAM-ER, which is specifically used on the NASAMS system. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-advanced-medium-range-air-air-missiles-extended-range
2024-07-17 | 138 | Hellfire Missiles (200); Advanced Precision Kill Weapon Systems (600) |  | Czech Republic | Europe (NATO) | No | Taiwan is not waiting on delivery of Hellfire or APKWS Missiles | https://www.dsca.mil/press-media/major-arms-sales/czech-republic-hellfire-missiles-and-advanced-precision-kill-weapon
2024-07-25 | 115 | GBU-53/B Small Diameter Bombs Increment II (196) | Various spare parts and support equipment | Belgium | Europe (NATO) | Yes (Partial) | Taiwan did not originally request ground-launched small diameter bombs in its HIMARS sale, but according to press reports the US agreed to sell Taiwan the capability, but has delayed delivery to get weapons to Ukraine | https://www.dsca.mil/press-media/major-arms-sales/belgium-small-diameter-bomb-increment-ii
2024-07-29 | 20 | Various MIDS JTRS Terminals (59) |  | Australia | Indo-Pacific | No | Amendment to FMS case initially reported to Congress in April 2022. | https://www.govinfo.gov/content/pkg/CREC-2024-07-29/pdf/CREC-2024-07-29.pdf
2024-07-29 | 26 | Excalibur Guided 155mm Artillery Shells (63) |  | Netherlands | Europe (NATO) | No | Amendment to FMS case initially reported to Congress in April 2020. | https://www.govinfo.gov/content/pkg/CREC-2024-07-29/pdf/CREC-2024-07-29.pdf
2024-07-31 | 600 | AH-1Z Attack Helicopters (12) | Helicopter Engines (26); Advanced Precision Kill Weapon System (APKWS) (1,680); Embedded GPS Systems (14); various radio and other equipment | Slovakia | Europe (NATO) | No | Taiwan's Army operates AH-1W helicopters but it is not currently waiting on delivery of AH-1Z. | https://www.dsca.mil/press-media/major-arms-sales/slovakia-ah-1z-attack-helicopters
2024-08-09 | 580 | HIMARS (16) | GMLRS Alternative Warhead pods (15); GMLRS Unitary pods (15); ATACMS (100) | Norway | Europe (NATO) | Yes | Taiwan is waiting on delivery of HIMARS launchers and munitions, including ATACMS | https://www.dsca.mil/press-media/major-arms-sales/norway-m142-high-mobility-artillery-rocket-systems
2024-08-13 | 18820 | F-15IA Fighter Aircraft (50) | Mid-Life Update kits for F-15I (25); F110-GE-129 Engines (120); APG-82(V)1 AESA (75); LANTIRN pods (50); LAU-128 AMRAAM launchers (320) | Israel | Middle East | No | Taiwan does not operate the F-15. | https://www.dsca.mil/press-media/major-arms-sales/israel-f-15ia-and-f-15i-aircraft
2024-08-13 | 102 | AIM-120C-8 AMRAAM (30) | AMRAAM control sections and containers; various spare parts and consumables | Israel | Middle East | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/israel-advanced-medium-range-air-air-missiles
2024-08-13 | 774 | 120mm tank cartridges (32,739) |  | Israel | Middle East | Yes (Primary) | 120mm tank shells are a component of the 2019 Abrams sale, though in a relativel small quantity compared to this sale. | https://www.dsca.mil/press-media/major-arms-sales/israel-120mm-tank-cartridges
2024-08-13 | 61 | 120mm mortar cartridges (50,000) |  | Israel | Middle East | No | There are no 120mm mortar cartridges in the Taiwan arms backlog. | https://www.dsca.mil/press-media/major-arms-sales/israel-m933a1-120mm-high-explosive-mortar-cartridges
2024-08-13 | 62 | Medium Tactical Vehicles |  | Israel | Middle East | No | Amendment to a previous arms sale for tactical vehicles. | https://www.dsca.mil/press-media/major-arms-sales/israel-m1148a1p2-family-medium-tactical-vehicles
2024-08-14 | 655 | C-17 Aircraft Contractor Logistical Support |  | United Kingdom | Europe (NATO) | No |  | https://www.govinfo.gov/content/pkg/CREC-2024-09-10/pdf/CREC-2024-09-10.pdf
2024-08-15 | 5000 | PAC-3 MSE missiles (600) | Various spares and support equipment. | Germany | Europe (NATO) | Yes (Primary) | Sale of 100 PAC-3 MSE interceptors to Taiwan announced in December 2022. | https://www.dsca.mil/press-media/major-arms-sales/germany-patriot-advanced-capability-3-missile-segment-enhancement
2024-08-15 | 85 | M1156 Precision Guidance Kits (5,832) | Ancillary items, compatability testing, firing tables, technical assistance and data. | Denmark | Europe (NATO) | No | The M1156 is used to turn 155mm shells into guided/smart weapons. | https://www.dsca.mil/press-media/major-arms-sales/denmark-precision-guidance-kits
2024-08-15 | 738 | MQ-9 Block 5 aircraft (6) | MQ-9 mobile ground stations (3); AN/DAS-4 Multi-spectral targeting systems (9); LYNX AN/APY-8 Block 20A Synthetic Aperture Radar with Maritime Wide Area Surveillance (9); various radio and communication systems. | Italy | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of 4 MQ-9B drones and associated support equipment. There may be some difference between the drone variants that Taiwan and Italy have purchased. | https://www.dsca.mil/press-media/major-arms-sales/italy-mq-9-block-5-aircraft
2024-08-16 | 265 | AIM-9X Block II+ Missiles (48) and AIM-9X Block II Missiles (120) | AIM-9X Block II Captive Air Training Missiles (48); AIM-9X Block II Special Air Training Missiles (48); Block II+ Tactical Guidance Units (4); Block II Tactical Guidance Units (12) | Canada | North America (NATO) | Yes (Primary) | Taiwan is waiting on delivery of AIM-9X Block II missiles. | https://www.dsca.mil/press-media/major-arms-sales/canada-aim-9x-sidewinder-block-ii-and-block-ii-tactical-missiles
2024-08-19 | 3500 | AH-64E Apache Helicopters (36) | Various helicopter subsystems and munitions. Including engines (76); Hellfire Missiles (456); AGM-179A Joint Air-to-Ground Missiles JAGM (152) | South Korea | Indo-Pacific | No | Taiwan operates the AH-64E, but it does not have any on order. | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-ah-64e-apache-helicopters
2024-08-19 | 100 | FGM-148F Javelin Missiles (350) |  | Australia | Indo-Pacific | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/australia-fgm-148f-javelin-missiles
2024-08-19 | 70 | M1156 Precision Guidance Kits (5,500) |  | Finland | Europe (NATO) | No | The M1156 is used to turn 155mm shells into guided/smart weapons. | https://www.dsca.mil/press-media/major-arms-sales/finland-m1156a1-precision-guidance-kits
2024-08-19 | 305 | CH-47 and AH-64 Helicopter Training |  | Netherlands | Europe (NATO) | No | Taiwan operates both the CH-47 and the AH-64, but helicopter training is not part of the backlog. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-ch-47-and-ah-64-helicopter-training
2024-08-20 | 110 | SAFE Archangel Boats |  | Tunisia | Middle East | No | Amendment to a previous sale for the same type of boat, which is used for offshore patrol and rescue. | https://www.dsca.mil/press-media/major-arms-sales/tunisia-65-safe-archangel-boats
2024-08-20 | 121 | M982A1 Excalibur 155mm shells (339) | Portable Electronic Fire Control Systems; Improved Platform Integration Kits; Simple Key Loaders; other spare parts | Denmark | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/denmark-excalibur-projectiles
2024-08-22 | 405 | AMRAAM-ER Missiles (100) | AMRAAM AIM-120C-8 guidance sections (4) | Norway | Europe (NATO) | Potential | Taiwan is waiting on delivery of AIM-120C-8s which are similar to but not exactly the same as the AMRAAM-ER, which is specifically used on the NASAMS system. | https://www.dsca.mil/press-media/major-arms-sales/norway-advanced-medium-range-air-air-missiles-extended-range
2024-08-22 | 592 | AIM-120C-8 Missiles (186) | AIM-120C-8 guidance sections (4) | Romania | Europe (NATO) | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/romania-aim-120-advanced-medium-range-air-air-missiles
2024-08-23 | 300 | AH-64E Sustainment Support Services |  | Australia | Indo-Pacific | No | Taiwan operates the AH-64E, but it does not have any on order. | https://www.dsca.mil/press-media/major-arms-sales/australia-ah-64e-apache-sustainment-support-services
2024-08-23 | 53 | Anti-Submarine Sonobuoys for MH-60R Helicopters |  | India | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/india-anti-submarine-warfare-sonobuoys
2024-08-29 | 224 | Patriot M903 Launching stations (2) | PAC-3 MSE launcher conversion kits; automated logistics systems; other upgrade equipment | Netherlands | Europe (NATO) | No | Taiwan is waiting for PAC-3 MSE interceptors but there are no launcher units in the backlog at this time. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-patriot-m903-launching-stations-new-buy-and-upgrades
2024-08-30 | 390 | HIMARS (8) | GMLRS Pods (48); Humvees of various configuration (10) | Croatia | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of HIMARS launchers and munitions, including GMLRS pods. | https://www.dsca.mil/press-media/major-arms-sales/croatia-m142-high-mobility-artillery-rocket-systems
2024-09-03 | 150 | AEGIS Class Destroyer Follow-On Technical Support |  | Japan | Indo-Pacific | No | Taiwan does not operate any ships equipped with the AEGIS system. | https://www.dsca.mil/press-media/major-arms-sales/japan-aegis-class-destroyer-follow-technical-support
2024-09-06 | 691 | AIM-9X Block II Missiles (246) | AIM-9X Block II Captive Air Training Missiles (6); AIM-9X Block II special air training missiles (2); AIM-9X Block II tactical guidance units (14) | Netherlands | Europe (NATO) | Yes (Primary) | Taiwan is waiting on delivery of AIM-9X Block II missiles. | https://www.dsca.mil/press-media/major-arms-sales/netherlands-aim-9x-sidewinder-block-ii-missiles
2024-09-09 | 133 | AIM-120C-8 AMRAAM (54) | AIM-120C-8 Guidance Sections (2); various other parts | Singapore | Indo-Pacific | Yes (Primary) | Taiwan purchased 200 AIM-120 C-8 missiles as part of a 2023 sale of F-16 munitions. | https://www.dsca.mil/press-media/major-arms-sales/singapore-aim-120c-8-advanced-medium-range-air-air-missiles
2024-09-12 | 165 | Heavy Duty Tank Trailers |  | Israel | Middle East | No | Addition to a previous FMS case. DSCA announcement mentions that deliveries are estimate to begin in 2027. | https://www.dsca.mil/press-media/major-arms-sales/israel-heavy-duty-tank-trailers
2024-09-13 | 4100 | KC-46A Aircraft (9) | PW4062 turbofan engines (18); AN/ALR-69A radar warning receivers (16); Large Aircraft Infrared Countermeasure assemblies (33) | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-kc-46a-aerial-refueling-aircraft
2024-09-13 | 7200 | F-35 Aircraft (32) | F135-PW-100 Engines (33); various other aircraft subsystems and related equipment | Romania | Europe (NATO) | No | The sale announcement does not mention specific munitions, which would be the most likely area of overlap with the Taiwan backlog. | https://www.dsca.mil/press-media/major-arms-sales/romania-f-35-aircraft
2024-09-20 | 114 | FGM-148F Javelin Missiles (218) | Javelin Lightweight Command Launch Units (107) | Bulgaria | Europe (NATO) | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/bulgaria-fgm-148f-javelin-missiles
2024-09-20 | 32 | AN/USQ-190 Multifunctional Information Distribution System, Joint Tactical Radio Systems (120) |  | Sweden | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/sweden-multifunctional-information-distribution-system-joint-tactical
2024-09-24 | 740 | Stinger Missiles for Avenger systems (720) |  | Egypt | Middle East | Yes (Primary) | Taiwan is waiting for Stinger missiles which should be delivered by the end of 2024 or first half of 2025. There may be some difference in the variant of Stinger. | https://www.dsca.mil/press-media/major-arms-sales/egypt-stinger-missiles
2024-09-24 | 39 | Follow on Technical Support for Vessel Maintenance and Repair |  | Iraq | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/iraq-follow-technical-support-vessel-maintenance-and-repair
2024-09-27 | 405 | AARGM-ER Missiles (100) | AARGM-ER Guidance Sections; AARM-ER Control Sections (24); Missile Containers | Australia | Indo-Pacific | Yes (Partial) | Taiwan has purchased AGM-88 missiles (HARMs), but they purchased a different variant (AGM-88B). Backlog is part of F-16 munitions sale in September 2022. | https://www.dsca.mil/press-media/major-arms-sales/australia-advanced-anti-radiation-guided-missiles-extended-range
2024-10-07 | 175 | Mk 54 Mod 0 Lightweight Torpedoes (53) | Exercise Torpedoes; air launch accessories; spare parts; contaners; technical support | India | Indo-Pacific | No | Taiwan purchased torpedo conversion kits in 2017, which have been delivered. | https://www.dsca.mil/press-media/major-arms-sales/india-mk-54-mod-0-lightweight-torpedoes
2024-10-07 | 680 | Electronic Attack Mission System EA-37B |  | Italy | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/italy-electronic-attack-mission-system
2024-10-07 | 110 | AN/MPQ-64 F1 Sentinel Radar Systems (4) |  | Romania | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/romania-sentinel-radar-systems
2024-10-11 | 252 | AIM-9X Block II Missiles (220) | Containers; support equipment; spare parts; missile software; technical assistance | Saudi Arabia | Middle East | Yes (Primary) | Taiwan is waiting on delivery of AIM-9X Block II missiles. | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-aim-9x-block-ii-sidewinder-missiles
2024-10-11 | 1200 | GMLRS Rocket Pods (259 pods, 1,554 missiles); ATACMS (203) |  | UAE | Middle East | Yes (Primary) | GMLRS and ATACMS are subcomponents of the two HIMARS sales, which should complete delivery by the end of 2026. | https://www.dsca.mil/press-media/major-arms-sales/united-arab-emirates-gmlrs-and-atacms-munitions
2024-10-11 | 139 | Ammunition for Artillery Systems, Machine Guns, and Tanks |  | Saudi Arabia | Middle East | Yes (Potential) | 105mm tank ammunition was part of Taiwan's Abrams FMS case. | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-ammunition-artillery-systems-machine-guns-and
2024-10-11 | 655 | AGM-114R3 Hellfire II Missiles (2,503) | Support and test equipment; spare and repair parts; technical documentation | Saudi Arabia | Middle East | No | Taiwan uses Hellfire missiles, but there are currently none of these missiles in the backlog. | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-agm-114r3-hellfire-ii-missiles
2024-10-16 | 1420 | AN/PRC-117G radios; AN/PRC-152A radios; AN/PRC-160 radios; AN/PRC-163 radios; AN/PRC-167 radios |  | Netherlands | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/netherlands-radio-equipment
2024-10-18 | 360 | Rolling Airframe Missile Block 2B (212) | RAM Guided Missiles Round Pack; Shipping and Storage Containers | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-rolling-airframe-missile-block-2b-tactical-missiles
2024-10-23 | 7300 | F-16 Viper Midlife Upgrade |  | Poland | Europe (NATO) | Yes (Primary) | Taiwan has mostly completed the upgrade of its existing F-16 fleet as of December 2023. However, Taiwan is waiting on delivery of the Viper Shield electronic warfare system, which is included in this sale. | https://www.dsca.mil/press-media/major-arms-sales/poland-f-16-viper-midlife-upgrade
2024-10-24 | 440 | TOW 2A Radio Frequency Missiles (507); TOW 2B Radio Frequency Missiles (507) |  | Saudi Arabia | Middle East | Yes (Primary) | Taiwan is waiting for delivery of 1,700 TOW-2B missiles, delivery of which is delayed. All missiles should arrive in Taiwan by end of 2025, potentially earlier. | https://www.dsca.mil/press-media/major-arms-sales/kingdom-saudi-arabia-tow-2a-tow-2b-missiles
2024-10-25 | 113 | Subsonic Seak-Skimming Aerial Targets | GQM-163 target drones | Japan | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/japan-subsonic-sea-skimming-aerial-targets-and-follow-technical
2024-10-28 | 450 | Patriot Sustainment |  | Switzerland | Europe (Non-NATO) | Yes (Potential) | Taiwan has past FMS cases for Patriot sustainment, but the backlog does not track maintenance sales. | https://www.dsca.mil/press-media/major-arms-sales/switzerland-patriot-sustainment
2024-10-29 | 744 | AMRAAM Missiles, AIM-120D-3 (203) | Guidance Sections (9); containers; spare parts | Denmark | Europe (NATO) | Yes (Potential) | Taiwan is waiting on delivery of two variants of the AMRAAM missile, but not this particular variant. | https://www.dsca.mil/press-media/major-arms-sales/denmark-aim-120d-3-advanced-medium-range-air-air-missiles
2024-10-30 | 941 | F-16 Aircraft Equipment and Support | F-16 Block 10/15 Aircraft (24 via third party transfer); AIM-120C-8 Missiles (36); MK-82 500 lb Bombs (102); other various munitions and equipment | Argentina | Latin America | Yes (Secondary) | Taiwan is waiting on delivery of AIM-120C-8s which are a component of this package. | https://www.dsca.mil/press-media/major-arms-sales/argentina-f-16-aircraft-equipment-and-support
2024-11-01 | 105 | Mobile Ground Control Approach Systems, GCA-2000 |  | Poland | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/poland-mobile-ground-control-approach-systems
2024-11-04 | 4920 | E-7 Airborne Early Warning and Control aircraft (4) | Jet Engines (8 installed, 2 spares); Guardian Laster Transmitter Assemblies; Large Aircraft Infrared Countermeasures Systems | South Korea | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-e-7-airborne-early-warning-control-aircraft
2024-11-05 | 184 | Large Enterprise Terminals System |  | Czech Republic | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/czech-republic-large-enterprise-terminals-system
2024-11-13 | 641 | Equipment to Modernize Hobart-class Destroyers and Hunter-Class Frigates | AN/WSN-12 Ring Laser Gyrocompasses (3); MIDS On-Ship Modernization Suites (3); MK 45 Lightweight Gun Carcasses (4); Tactical Tomahawk Weapons Control Systems (3) | Australia | Indo-Pacific |  | Amendment to a 2020 FMS case for surface warship upgrades. | https://www.govinfo.gov/content/pkg/CREC-2024-11-13/pdf/CREC-2024-11-13.pdf
2024-11-13 | 1930 | Equipment to Upgrade up to 6 P-8A Aircraft |  | Norway | Europe (NATO) | No | Amendment to a 2016 FMS case for P-8A anti-submarine aircraft to Norway. This amendment provides for additional equipment upgrades and follow-on support. | https://www.govinfo.gov/content/pkg/CREC-2024-11-13/pdf/CREC-2024-11-13.pdf
2024-11-13 | 50 | Equipment for MH-60R Helicopters |  | Spain | Europe (NATO) | No | Amendment to a 2022 FMS case for MH-60R Helicopters. This amendment replaces the engines in the original case with a newer model, and some new subsystems. | https://www.govinfo.gov/content/pkg/CREC-2024-11-13/pdf/CREC-2024-11-13.pdf
2024-11-14 | 160 | F-16 Engine Follow-On Support |  | Greece | Europe (NATO) | Yes (Partial) | Taiwan has several FMS cases for spare and repair parts for F-16 aircraft that would likely overlap with this sale. However, Taiwan's maintenance FMS cases are not included in our dataset's figure for the backlog. | https://www.dsca.mil/press-media/major-arms-sales/greece-f-16-engine-follow-support
2024-11-18 | 70 | Tactical Combat Training System Increment II (46) |  | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-tactical-combat-training-system-increment-ii
2024-11-19 | 6200 | F-15K Aircraft Upgrade |  | South Korea | Indo-Pacific | No | Upgrade program for South Korea's entire F-15 fleet. Includes AESA radars, electronic warfare suite, and mission computers | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-f-15k-aircraft-upgrade
2024-11-19 | 100 | Sustainment of US Army Supplied Systems |  | Ukraine | Europe (Non-NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/ukraine-blanket-order-sustainment-us-army-supplied-systems-0
2024-11-20 | 403 | Equipment for Saudi Naval Expansion Program | RGM-114-L Hellfire Missiles (148); Indra Rigel Electronic Attack Systems (5); M240B Machine Guns (16) | Saudi Arabia | Middle East | No | Amendment to 2015 FMS case to sell frigates to Saudi Arabia. This amendment adds over 100 Hellfire missiles, machine guns, and electronic warfare systems. | https://www.govinfo.gov/content/pkg/CREC-2024-11-20/pdf/CREC-2024-11-20.pdf
2024-11-20 | 71 | Equipment for MH-60R Helicopters | Advanced Precision Kill Weapons System rockets (682); AGM-114R Hellfire Missiles (153); M240D machine gun (1) | Saudi Arabia | Middle East | No | Amendment to 2015 FMS case to sell MH-60R Helicopters to Saudi Arabia. This amendment covers precise rocket systems and Hellfire missiles. | https://www.govinfo.gov/content/pkg/CREC-2024-11-20/pdf/CREC-2024-11-20.pdf
2024-11-21 | 174 | AIM-120D AMRAAM (56); AIM-120 AMRAAM Guidance Sections (4) |  | United Kingdom | Europe (NATO) | Yes (Primary) | Amendment to 2018 FMS case for AIM-120 missiles. This amendment adds missiles to the original case. Taiwan is waiting for delivery of AIM-120s as part of an FMS case for F-16 munitions. | https://www.govinfo.gov/content/pkg/CREC-2024-11-21/pdf/CREC-2024-11-21.pdf
2024-11-27 | 125 | High Gain Measurement System (HGMS) | Off-Aspect Mid-Frequency Line Arrays (MFLAs) | United Kingdom | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/united-kingdom-high-gain-measurement-system
2024-12-02 | 1170 | MH-60R Helicopters (30) |  | India | Indo-Pacific | No |  | https://www.dsca.mil/press-media/major-arms-sales/india-mh-60r-multi-mission-helicopter-equipment-and-follow-support
2024-12-03 | 108 | Javelin FGM-184F Missiles (184) | Javelin Lightweight Command Launch Units (30) | Tunisia | Middle East | No | Javelin missiles were previously in the Taiwan backlog, but completed delivery in the summer of 2024. | https://www.dsca.mil/press-media/major-arms-sales/tunisia-javelin-missiles
2024-12-06 | 807 | AIM-120D3 AMRAAM (226) | AIM-120D3 Guidance Sections (5); AIM-120 AMRAAM Integrated Test Vehicle (1) | The Netherlands | Europe (NATO) | Yes (Partial) | Taiwan is waiting on delivery of AMRAAM missiles, from an F-16 munition sale and a NASAMS sale, but Taiwan is waiting for different variants than the AIM-120D3 | https://www.dsca.mil/press-media/major-arms-sales/netherlands-aim-120d3-advanced-medium-range-air-air-missiles
2024-12-10 | 300 | Maintenance Repair Sustainment Capability |  | Kuwait | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kuwait-maintenance-repair-sustainment-capability
2024-12-10 | 266 | F-16 Sustainment Services |  | Ukraine | Europe (Non-NATO) | Yes (Partial) | The US has sold Taiwan several FMS cases of F-16 spare parts and other sustainment services in recent years. Neither the Ukraine sale nor the Taiwan sales specify all the various equipment. There is a possibility of overlapping equipment, but not possible to confirm. | https://www.dsca.mil/press-media/major-arms-sales/ukraine-f-16-sustainment-services
2024-12-16 | 300 | KDX-II Product Improvement Program |  | South Korea | Indo-Pacific | Yes (Potential) | This FMS case is for upgraded equipment for large South Korean surface warships. The US has recently done FMS cases for support of Taiwan's large surface warships. But it is not clear if there is overlapping equipment. | https://www.dsca.mil/press-media/major-arms-sales/republic-korea-kdx-ii-class-destroyers-product-improvement-program
2024-12-17 | 130 | M1156A1 Precision Guidance Kit Fuzes (8,001) |  | Norway | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/norway-m1156a1-precision-guidance-kits-fuzes
2024-12-18 | 4030 | Logistics Support for C-17 Globemasters |  | Australia | Indo-Pacific | No | Amendment to a July 2009 FMS case for logistics support for C-17 aircraft. | https://www.govinfo.gov/content/pkg/CREC-2024-12-18/pdf/CREC-2024-12-18.pdf
2024-12-20 | 130 | Aerosonde Uncrewed Aircraft Systems |  | Greece | Europe (NATO) | No |  | https://www.dsca.mil/press-media/major-arms-sales/greece-aerosonde-uncrewed-aircraft-systems-and-armored-security
2024-12-20 | 4690 | Upgrade of M1A1 Tanks (555) | Driver Vision Enhancer Kits; Thermal Imaging System gunner sights; smoke grenade launchers; AGT-1500 tank engines; X-1100 tank transmissions | Egypt | Middle East | Yes (Potential) | Taiwan recently took delivery of a first batch of Abrams tanks. This FMS case should not impact the Taiwan Abrams case, but it could have knock-on effects for maintenance/sustainment in the future. However, Taiwan did purchase a different variant of the Abrams than this one. | https://www.dsca.mil/press-media/major-arms-sales/egypt-abrams-tank-refurbishment-support-and-equipment
2024-12-20 | 30 | Advanced Precision Kill Weapon Systems (543) |  | Egypt | Middle East | No | Amendment to early FMS case for APKWS. $30 million represents new FMS total value, which is for 759 APKWS. | https://www.dsca.mil/press-media/major-arms-sales/egypt-advanced-precision-kill-weapon-system-apkws
2024-12-20 | 630 | AGM-114R Missiles (2,183) |  | Egypt | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/egypt-hellfire-agm-114r-missiles
2024-12-20 | 88 | AIM-120C-8 AMRAAM (30) | AMRAAM Guidance Section (1) | Morocco | Middle East | Yes (Primary) | Taiwan is waiting for delivery of two variants of AMRAAM missiles from a sale of F-16 munitions and the sale of NASAM batteries. | https://www.dsca.mil/press-media/major-arms-sales/kingdom-morocco-advanced-medium-range-air-air-missiles
2024-12-20 | 86 | GBU-39B Small Diameter Bombs (500) |  | Morocco | Middle East | No |  | https://www.dsca.mil/press-media/major-arms-sales/kingdom-morocco-gbu-39b-small-diameter-bombs-sdb-i

## Contract Award Announcements
Date of Award | Capability | Related Backlog Item | Other FMS Customers | Date of Completion | FMS Obligated (millions) | Total Contract (Millions) | Source
2023-06-28 | Engine Support for F-16 Aircraft | F-16 | Yes | 2026-06-30 | N/A | 22.89 | https://www.defense.gov/News/Contracts/Contract/Article/3442962/
2023-06-30 | Logistics Services (system not specified) | N/A | No | 2026-12-31 | 14.29 | 14.29 | https://www.defense.gov/News/Contracts/Contract/Article/3446601/
2023-07-28 | Support Services for Legacy Rotating Guided Missile Launching System | N/A | No | 2024-07-01 | 0.55 | 8.76 | https://www.defense.gov/News/Contracts/Contract/Article/3475675/
2023-07-31 | PAC-3 Production | PAC-3 MSE Interceptors | Yes | 2032-12-31 | 556.11 | 556.11 | https://www.defense.gov/News/Contracts/Contract/Article/3477441/
2023-08-31 | F-16 Support | Peace Phoenix Rising | No | 2030-08-30 | 4.54 | 18.17 | https://www.defense.gov/News/Contracts/Contract/Article/3513182/
2023-09-05 | Mission Planning and Support Services | N/A | Yes | 2034-09-04 | N/A | 600 | https://www.defense.gov/News/Contracts/Contract/Article/3515896/
2023-09-18 | Logistics Support Services for Utility Helicopters Office | N/A | Yes | 2024-09-17 | 8.04 | 8.04 | https://www.defense.gov/News/Contracts/Contract/Article/3529558/
2023-09-18 | Logistics Support (Likely for Helicopters) | N/A | Yes | 2024-09-17 | 8.04 | 8.04 | https://www.defense.gov/News/Contracts/Contract/Article/3529558/
2023-09-27 | Abrams Transmissions and System Technical support Services | Abrams Tanks | Yes | 2024-12-31 | 83.35 | 83.35 | https://www.defense.gov/News/Contracts/Contract/Article/3540301/
2023-09-29 | Joint Helmet Mounted Cueing System Repairs (F-16s in Taiwan's Case) | Aircraft Maintenance and Spares* | Yes | 2026-09-28 | N/A | 25.84 | https://www.defense.gov/News/Contracts/Contract/Article/3543791/
2023-11-06 | Software Engineering Services for Submarines | N/A | No | 2026-11-01 | 16.25 | 36.26 | https://www.defense.gov/News/Contracts/Contract/Article/3581601/
2023-11-09 | Spare Parts for F-16 | Aircraft Maintenance and Spares | Yes | 2033-11-03 | 0.91 | 238 | https://www.defense.gov/News/Contracts/Contract/Article/3585521/
2023-12-04 | Program Support Services for Utility Helicopters Office | N/A | Yes | 2024-09-30 | 10.6 | 10.6 | https://www.defense.gov/News/Contracts/Contract/Article/3606232/
2024-01-11 | Non-Recurring Engineering for Harpoon Coastal Defense System | Harpoon Coastal Defense System | No | 2025-01-01 | 6.9 | 14.1 | https://www.defense.gov/News/Contracts/Contract/Article/3643583/
2024-01-23 | Mission Planning and Support Services | N/A | Yes | 2024-12-31 | N/A | 40 | https://www.defense.gov/News/Contracts/Contract/Article/3653384/
2024-02-02 | AGM-154 Block III (50) | AGM-154 JSOW | No | 2028-03-01 | 48.8 | 68.4 | https://www.defense.gov/News/Contracts/Contract/Article/3665263/
2024-03-12 | MQ-9B Procurement | MQ-9B | No | 2027-08-11 | 120 | 250 | https://www.defense.gov/News/Contracts/Contract/Article/3704846/
2024-03-29 | F-16 CORE Sustainment | Aircraft Maintenance and Spares | Yes | 2025-02-28 | 33.8 | 33.8 | https://www.defense.gov/News/Contracts/Contract/Article/3725457/
2024-04-19 | E-2C/D Sustainment and Technical Support | Aircraft Maintenance and Spares | Yes | 2025-04-01 | 11.5 | 26.2 | https://www.defense.gov/News/Contracts/Contract/Article/3749216/
2024-04-24 | Engine Support for F-15 and F-16 Aircraft | Aircraft Maintenance and Spares | Yes | 2026-03-15 | 1.13 | 13.75
2024-05-29 | Technical Support for the Utility Helicopters Office | N/A | Yes | 2025-06-08 | N/A | 29.83 | https://www.defense.gov/News/Contracts/Contract/Article/3790490/
2024-06-11 | HCDS Non-Recurring Engineering Support | Harpoon Coastal Defense System | No | 2026-08-01 | 81.06 | 81.06 | https://www.defense.gov/News/Contracts/Contract/Article/3803321/
2024-06-11 | Non-Recurring Engineering for Harpoon Coastal Defense System | Harpoon Coastal Defense System | No | 2026-08-01 | 81.06 | 81.06 | https://www.defense.gov/News/Contracts/Contract/Article/3803321/
2024-06-21 | DB-110 and MS-110 Sustainment | MS-110 Reconnaissance Pod | Yes | 2027-06-30 | 2.29 | 264.59 | https://www.defense.gov/News/Contracts/Contract/Article/3814112/
2024-06-27 | Harpoon Coastal Defense System Launcher Configuration Changes | Harpoon Coastal Defense System | No | 2028-09-01 | 5.38 | 10.98 | https://www.defense.gov/News/Contracts/Contract/Article/3819954/
2024-07-02 | Viper Shield Electronic Warfare Suite | F-16 | No | 2028-06-30 | 177.7 | 897.4 | https://www.defense.gov/News/Contracts/Contract/Article/3825673/
2024-07-12 | Support for Guided Missile Launching | N/A | Yes | 2025-07-01 | 0.29 | 9.01 | https://www.defense.gov/News/Contracts/Contract/Article/3837552/
2024-07-26 | F-16 Block 70 Training Simulator Program | F-16 | No | 2026-04-30 | 35.17 | 58.29 | https://www.defense.gov/News/Contracts/Contract/Article/3851872/
2024-09-20 | Universal Water Activated Release System (for aircraft ejection systems) | N/A | Yes | 2025-09-01 | 8.84 | 8.84 | https://www.defense.gov/News/Contracts/Contract/Article/3913138/
2024-11-20 | Support of Multiple Mission Planning Systems | N/A | Yes | 2034-12-31 | N/A | 600 | https://www.defense.gov/News/Contracts/Contract/Article/3973445/
2024-12-11 | F-16 Sustainment Support | F-16 | No | 2034-05-31 | 1.6 | 987 | https://www.defense.gov/News/Contracts/Contract/Article/3997747/
2024-12-16 | Mission Planning and Support Services | N/A | Yes | 2025-12-31 | N/A | 40 | https://www.defense.gov/News/Contracts/Contract/Article/4005907/
2024-12-17 | System Engineering and Integration | N/A | Yes | 2026-12-07 | N/A | 360 | https://www.defense.gov/News/Contracts/Contract/Article/4008415/
2025-01-30 | F-16 Training Simulators | N/A | No | 2026-12-31 | 8.83 | 18.37 | https://www.defense.gov/News/Contracts/Contract/Article/4048633/
2025-01-31 | F-110-GE-129 Engine Component Spares and Consumables | F-16 Maintenance | No | 2025-12-31 | 8.42 | 11.22 | https://www.defense.gov/News/Contracts/Contract/Article/4049800/
2025-02-03 | Standard Missile Items | SM-2(?) | Yes | 2029-05-01 | 10.16 | 12.16 | https://www.defense.gov/News/Contracts/Contract/Article/4051668/
2025-03-12 | AMRAAM C8 and D3 Risk Reduction | F-16 Munitions | Yes | 2027-08-06 | 92 | 92 | https://www.defense.gov/News/Contracts/Contract/Article/4117765/
2025-04-01 | AMRAAM C8 and D3 Variants | F-16 Munitions | Yes | 2026-05-31 | 11.53 | 2440 | https://www.defense.gov/News/Contracts/Contract/Article/4142257/
2025-04-02 | E-2C/D Sustainment and Technical Support | N/A | Yes | 2026-04-01 | 11.5 | 24.11 | https://www.defense.gov/News/Contracts/Contract/Article/4143747/
2025-05-07 | AMRAAM C8 and D3 Variants | F-16 Munitions | Yes | 2027-12-31 | 3.27 | 13.86 | https://www.defense.gov/News/Contracts/Contract/Article/4177700/
2025-05-20 | F-16 Block 70 Training Simulator Program | F-16 | No | 2028-01-31 | 8.38 | 66.66 | https://www.defense.gov/News/Contracts/Contract/Article/4193237/
2025-07-29 | Rotating Guided Missile Launching Systems | N/A | No | 2026-07-01 | 0.15 | 9.22 | https://www.defense.gov/News/Contracts/Contract/Article/4258695/
2025-07-31 | AMRAAM Production Lots 39 and 40 | F-16 Munitions; NASAMS | Yes | 2031 | 621 | 3500 | https://www.defense.gov/News/Contracts/Contract/Article/4261297/
2025-08-29 | F-16 Sustainment Support | F-16 | Yes | 2026-01-31 | N/A | 43 | https://www.war.gov/News/Contracts/Contract/Article/4290468/
2025-09-02 | HAWK Support | N/A | Yes | 2026-09-03 | 12.74 | 12.74 | https://www.war.gov/News/Contracts/Contract/Article/4291594/
2025-09-09 | AMRAAM Support | F-16 Munitions; NASAMS | Yes | 2030-09-07 | 0.35 | 760 | https://www.war.gov/News/Contracts/Contract/Article/4298387/
2025-09-25 | Abrams Technical Support | Abrams Tanks | Yes | 2027-02-27 | 26.85 | 26.85 | https://www.war.gov/News/Contracts/Contract/Article/4315371/
2025-09-25 | Taiwan Early Warning Radar | N/A | No | 2027-12-31 | N/A | 15.16 | https://www.war.gov/News/Contracts/Contract/Article/4315371/
2025-09-29 | Spare Parts for Torpedoes | Mk 48 Torpedoes | Yes | 2029-12-01 | 2.29 | 10.88 | https://www.war.gov/News/Contracts/Contract/Article/4317777/
2025-09-30 | AMRAAM Production Modification | F-16 Munitions; NASAMS | Yes | 2030-05-30 | 9.16 | 41.68 | https://www.war.gov/News/Contracts/Contract/Article/4319114/
2025-09-30 | AMRAAM Production Modification | F-16 Munitions; NASAMS | Yes | 2027-12-31 | 3.28 | 11.16 | https://www.war.gov/News/Contracts/Contract/Article/4319114/
2025-11-13 | F-16 System Program Office FMS Support | F-16; F-16 Munitions | Yes | 2030-11-30 | 2.7 | 303.6 | https://www.war.gov/News/Contracts/Contract/Article/4330947/contracts-for-nov-13-2025/
2025-11-17 | NASAMS Fire Unit Procurement | NASAMS | No | 2031-02-28 | 698.95 | 698.95 | https://www.war.gov/News/Contracts/Contract/Article/4333778/contracts-for-nov-17-2025/
2025-12-04 | MQ-9B Processing Exploitation Data (PED) Ground Station Procurement | MQ-9B | No | 2028-01-31 | 8.27 | 23.4 | https://www.war.gov/News/Contracts/Contract/Article/4349976/contracts-for-dec-4-2025/
2025-12-31 | Sniper, IRST, and LANTIRN Targeting Pod Procurement | F-16 IRST | No | 2031-06-30 | 157.3 | 328.5 | https://www.war.gov/News/Contracts/Contract/Article/4369702/contracts-for-dec-31-2025/
2026-01-21 | PAC-3 Inspection, Repair, Recertification | N/A | No | 2028-06-30 | 52.38 | 202.78 | https://www.war.gov/News/Contracts/Contract/Article/4384469/contracts-for-jan-21-2026/
2026-01-29 | F-16 Block 70 Training Simulator Procurement | F-16 | No | 2028-08-29 | 59.42 | 69.88 | https://www.war.gov/News/Contracts/Contract/Article/4393248/contracts-for-jan-29-2026/
2026-02-23 | F-16 Commodities Sustainment | F-16 | Yes | 2037-02-28 | N/A | 98.87 | https://www.war.gov/News/Contracts/Contract/Article/4412484/contracts-for-feb-23-2026/
2026-02-25 | Utility Helicopters Project Office Support | N/A | Yes | 2026-09-07 | 18.99 | 211.24 | https://www.war.gov/News/Contracts/Contract/Article/4414615/contracts-for-feb-25-2026/
2026-03-17 | F100 Engine Module Re-Manufacturing | F-16 | Yes | 2029-03-16 | N/A | 470 | https://www.war.gov/News/Contracts/Contract/Article/4436603/contracts-for-march-17-2026/
2026-04-15 | AMRAAM-ER Transition to Production | F-16 Munitions | Yes | 2030-04-13 | 61.57 | 234.76 | https://www.war.gov/News/Contracts/Contract/Article/4459874/contracts-for-april-15-2026/
2026-04-15 | F-100-PW-220 Engine Stator and Shroud Re-Manufacturing | F-16 | Yes | 2027-04-13 | N/A | 13.72 | https://www.war.gov/News/Contracts/Contract/Article/4459874/contracts-for-april-15-2026/
2026-04-29 | HIMARS Production | HIMARS | Yes | 2028-04-30 | N/A | 1132.45 | https://www.war.gov/News/Contracts/Contract/Article/4473550/contracts-for-april-29-2026/

## Trump Biden Comparison
Date of Sale | Capability Sold | Dollar Value (in Millions) | Weapon Category
TRUMP
2019-07-08 | Stinger Missiles | 223 | Asymmetric
2019-07-08 | TOW-2B Missiles | 241 | Asymmetric
2019-07-08 | Javelin Missiles | 129 | Asymmetric
2020-10-21 | HIMARS | 436 | Asymmetric
2020-10-26 | Harpoon Coastal Defense System | 2370 | Asymmetric
2020-11-03 | MQ-9B Drones | 600 | Asymmetric
2020-12-07 | Field Information Communications System | 280 | Asymmetric
2017-06-29 | Surveillance Radar Program Support | 400 | Maintenance
2018-09-24 | Foreign Military Sales Order II Case | 330 | Maintenance
2019-04-15 | CONUS Based F-16 Training | 500 | Maintenance
2020-07-09 | PAC-3 Repair and Recertification | 620 | Maintenance
2017-06-29 | AGM-88B HARM Missiles | 147 | Munition
2017-06-29 | SM-2 Block IIIA Missiles | 125 | Munition
2017-06-29 | MK 48 Heavyweight Torpedo | 250 | Munition
2017-06-29 | MK 54 Lightweight Torpedo Kits | 175 | Munition
2017-06-29 | AGM-154C JSOW | 186 | Munition
2020-05-20 | MK 48 Heavyweight Torpedo | 180 | Munition
2020-10-21 | SLAM-ER Missiles | 1008 | Munition
2017-06-29 | AN/SLQ-32 Upgrade | 80 | Traditional
2019-07-08 | Abrams Tanks | 2000 | Traditional
2019-08-20 | F-16 C/D Block 70 | 8000 | Traditional
2020-10-21 | MS-110 Recce Pod | 367 | Traditional
2025-11-13 | Non-Standard Spare and Repair Parts | 330 | Maintenance
Trump Asymmetric Total | 4279 | 7 sales
Trump Maintenance Total | 2180 | 5 sales
Trump Munition Total | 2071 | 7 sales
Trump Traditional Total | 10447 | 4 sales
BIDEN
2022-09-02 | Air-Launched Harpoon Missiles | 355 | Asymmetric
2022-12-05 | PAC-3 MSE Missiles | 882 | Asymmetric
2022-12-05 | HIMARS | 520 | Asymmetric
2022-12-28 | Volcano Anti-Tank Mining System | 180 | Asymmetric
2024-02-21 | Tactical Data Link System Upgrade | 75 | Asymmetric
2024-06-18 | Switchblade 300 | 60 | Asymmetric
2024-06-18 | Altius-600M UAVs | 300 | Asymmetric
2024-10-25 | NASAMS | 1160 | Asymmetric
2024-10-25 | AN/TPS-77 and AN/TPS-78 Radar | 828 | Asymmetric
2024-12-20 | C4 Modernization | 265 | Asymmetric
2022-02-07 | IESP and FSP Support | 100 | Maintenance
2022-04-05 | Contractor Technical Assistance | 95 | Maintenance
2022-06-08 | Ship Spare Parts | 120 | Maintenance
2022-07-15 | Blanket Order Contractor Technical Assistance | 108 | Maintenance
2022-09-02 | Logistics Support for Suveillance Radar Program | 665 | Maintenance
2022-12-06 | Aircraft Spare Parts, Non-Standard | 98 | Maintenance
2022-12-06 | Aircraft Spare Parts, Standard | 330 | Maintenance
2023-06-29 | Cooperative Logistics Supply Support | 108 | Maintenance
2023-12-15 | C4 Life Cycle Support | 300 | Maintenance
2024-06-05 | F-16 Spare Parts, Non-Standard | 80 | Maintenance
2024-06-05 | F-16 Spare Parts, Standard | 220 | Maintenance
2024-09-16 | Spare Parts | 228 | Maintenance
2024-11-29 | F-16 and AESA Logistics Support | 320 | Maintenance
2024-11-29 | Improved Mobile Suscriber Follow-On Support | 42 | Maintenance
2024-12-03 | CONUS F-16 Training Support | 7 | Maintenance
2022-09-02 | AIM-9X Missiles | 86 | Munition
2023-03-01 | F-16 Munitions | 619 | Munition
2023-06-29 | 30mm Ammunition | 332 | Munition
2023-08-23 | F-16 IRST Systems | 500 | Traditional
2024-12-20 | MK 75 76mm Gun Mounts | 30 | Traditional
Biden Asymmetric Total | 4625 | 10 sales
Biden Maintenance Total | 2814 | 15 sales
Biden Munitions Total | 1037 | 3 sales
Biden Traditional Total | 530 | 2 sales